## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for RAMMAKHALER CHAK PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016316] | AE SWSD-II | JE1 | ORD/000552/2022-2023 | 3041/SWD-I | 20/02/2023 | 22/03/2023 | PADMA ENGINEERING CO. | 15.9 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Rammakhaler Chak water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000513/2022-2023 | 352/SMD | 09/02/2023 | 10/05/2023 | S.P. CONSTRUCTION | 23.29 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Preparation and submission of Detailed Project Report of RAMMAKHALER CHAK AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000421/2021-2022 | 1973/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.83 | 2.75 | 97.38 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 36.66 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Land Development at 2nd Tubewell site of Rammakhaler Chak Piped Water Supply Scheme under proposed ground water based Rammakhaler Chak PWSS to accommodate FHTC in Bishnupur-I Block, District-South 24-Pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/13784) |  |  | ORD/000756/2023-2024 | 656/SWD-I | 06/02/2024 | 21/02/2024 | N ENTERPRISE | 3.97 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design, construction of Boundary wall, Pump House for RAMMAKHALER CHAK PWSS of Bishnupur-I Block under South 24 Parganas W/S Division-I, PHE Dte., Dist.-South 24 Parganas. | AE SWSD-II | JE1 | ORD/000275/2024-2025 | 2925/SWD-I | 25/06/2024 | 21/04/2025 | M/S SUBHODEEP ENTERPRISE | 140.22 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RAMMAKHALER CHAK PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016316] | AE SWSD-II | JE1 | ORD/000601/2022-2023 | 3129/SWD-I | 24/02/2023 | 26/03/2023 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 14.37 | 90.47 | 98
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Additional quotation for new service connection at Rammakhalerchak PWSS P.H. No. I under Bishnupur- I Block. Ref. ID- 860294797, Application ID- 100000102977 Application date- 18/03/2024 |  |  | BILL/00393/2024-2025 | BP-2024-25-102 | 10/06/2024 | 10/06/2024 | WBSEDCL | 0.28 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04615/2023-2024 | BP-2023-24-476 | 02/02/2024 | 02/02/2024 | WBSEDCL | 3.64 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of RAMMAKHALER CHAK PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 1749) [TSM/016316]. | AE S24D1,AE SWSD-II | JE1 | ORD/000076/2023-2024 | 390/SWD-I | 28/04/2023 | 01/05/2025 | MALAY KANTI DEY | 261.78 | 54.72 | 20.9 | 61
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 19/03/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Rammakhaler chak piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. | SM/13784 | Augmentation | Laying rising main and additional distribution pipeline, Construction of approach road, protection of pipeline and other allied works for Rammakhaler Chak PWSS of Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (SM/13784) | AE SWSD-II | JE1 | ORD/000414/2024-2025 | 3730/SWD-I | 27/08/2024 | 11/10/2024 | MALAY KANTI DEY | 65.01 | 0 | 0 | 4
Total | [13 empty] | 674.94 | 71.85 | 10.64