## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 286/SWD-I | 24/04/2023 |  | Resource Division | 57.09 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000254/2023-2024 | 1006/SWD-1 | 09/06/2023 |  | Resource Division | 12.56 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities under the Assistant Engineers (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I |  | ORD/000876/2022-2023 | 3729/SWD-I | 31/03/2023 | 30/09/2023 | DIPAK NASKAR | 0.87 | 0.38 | 44.17 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities under the Assistant Engineers (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] |  |  | ORD/000096/2023-2024 | 787/SWD-I | 04/05/2023 | 03/11/2023 | DIPAK NASKAR | 0.87 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2039] | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000437/2023-2024 | 2012/SWD-I | 28/08/2023 | 23/06/2024 | MILAN GHOSH | 472.62 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR RAGHUNATHPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016318) | AE HQ-I | JE-3 | ORD/000348/2022-2023 | 2168/SWD_I | 09/12/2022 | 08/01/2023 | PADMA ENGINEERING CO. | 30.07 | 12.02 | 39.96 | 50
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAGHUNATHPUR PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13785] | AE HQ-I |  | ORD/000769/2022-2023 | 3643/SWD-I | 28/03/2023 | 12/04/2023 | PADMA ENGINEERING CO. | 3.14 | 1.57 | 50 | 50
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2023 to 30.11.2023) [SM/13785] | AE HQ-I |  | ORD/000178/2023-2024 | 779/SWD-I | 31/05/2023 | 30/11/2023 | MINTU SOMADDAR | 0.87 | 2.03 | 233.39 | 20
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04656/2023-2024 | BP-2023-24-491 | 12/02/2024 |  | WBSEDCL | 4.62 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Raghunathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000336/2022-2023 | 3740/SMD | 29/12/2022 | 29/03/2023 | T.S. CONSTRUCTION | 22.36 | 5 | 22.34 | 35
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.12.2023 to 31.05.2024) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-II | JE-3 | ORD/000702/2023-2024 | 3000/SWD-I | 29/11/2023 | 30/05/2024 | MINTU SOMADDAR | 0.87 | 1.6 | 184.02 | 20
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Raghunathpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002407/2023-2024 | 278/SMSD | 29/02/2024 | 15/03/2024 | T.S. CONSTRUCTION | 0.9 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RAGHUNATHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13785 | Augmentation | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2024 to 30.11.2024) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-II,Assistant engineer (contractual) | JE-3 | ORD/000218/2024-2025 | 2482/SWD-I | 28/05/2024 | 27/11/2024 | MINTU SOMADDAR | 0.87 | 1.6 | 184.03 | 18
Total | [13 empty] | 607.7 | 24.19 | 3.98