## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 21.88 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000237/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 17.69 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016148) | AE HQ-I | JE-3 | ORD/000354/2022-2023 | 2261/SWD_I | 15/12/2022 | 14/01/2023 | SAHI MASUM | 29.69 | 28.37 | 95.55 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAMCHANDRAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13786] | AE HQ-I | JE-3 | ORD/000721/2022-2023 | 3561/SWD-I | 22/03/2023 | 06/04/2023 | SAHI MASUM | 3.14 | 3.14 | 100 | 50
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ramchandrapur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002341/2023-2024 | 262/SMSD | 23/02/2024 | 09/03/2024 | PS & ASSOCIATES | 0.92 | 0.89 | 97.12 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04655/2023-2024 | BP-2023-24-490 | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Charges for New service connection at Pump house no-2 of Ramchandrapur (Sonarpur Block) |  |  | BILL/00518/2024-2025 | BP-2024-25-125 | 24/06/2024 | 24/06/2024 | WBSEDCL | 4.19 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAMCHANDRAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2871] | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000665/2022-2023 | 3386/SWD-I | 10/03/2023 | 12/12/2025 | BALAJI UDYOG | 455.95 | 162.62 | 35.67 | 33
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Restoration of Road at Publi Garden, Nil Mrittika (NP-1-5, 73-90, 112-90, 90-105, 90-115, 115-120, 151-115, 93-151, 151-154, 122-266, 266-267, 249-266, 27-43, 19-33, 25-50 & 9-18) of RAMCHANDRAPUR Piped Water Supply Scheme, Block- Sonarpur under South 24 Pgns W/S Division-I, PHE Dte. (SM/13786) | Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000551/2024-2025 | 4224/SWD-I | 30/09/2024 | 29/04/2025 | BALAJI UDYOG | 19.97 | 0 | 0 | 80
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Construction of Boundary Wall, Pathway, Drain and Development of Land & others allied works of ¿RAMCHANDRAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13786). | Assistant engineer (contractual) | JE RWS, Sonarpur Block,JE-3 | ORD/000238/2024-2025 | 2658/SWD-I | 07/06/2024 | 22/07/2024 | BALAJI UDYOG | 67.34 | 0 | 0 | 33
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Laying of additional pipeline at Ramchandrapur PWSS to accommodate FHTC in Sonarpur Block under south 24 Parganas W/S Division-I under JalJeevan Mission. [SM Code - SM/13786] | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000855/2023-2024 | 1325/SWD-I | 15/03/2024 | 26/04/2025 | BALAJI UDYOG | 21.72 | 0 | 0 | 80
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Restoration of PWD Road damaged due to laying of HDPE pipe line from chainage 0.280Kmp to 1.110 (L/S, R/S, C/L) Kmp of Narendrapur More N.S Road to EM Bye pass, Ramchandrapur, Dhamaitola Payra bagan, Karbala School Road under RAMCHANDRAPUR PWSS to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District (SM/13786) |  |  | ORD/000744/2024-2025 | 4666/SWD-I | 18/11/2024 | 18/12/2024 | BALAJI UDYOG | 26.02 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | RAMCHANDRAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13786 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramchandrapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000337/2022-2023 | 3741/SMD | 29/12/2022 | 16/03/2025 | M/S. PS & ASSOCIATES | 26.01 | 11.88 | 45.66 | 100
Total | [13 empty] | 698.65 | 206.9 | 29.61