## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Samukhpota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000338/2022-2023 | 3742/SMD | 29/12/2022 | 29/03/2023 | CMS ENGINEERING CONCERN | 26.76 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 54.07 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 10.87 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24- Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1764] | AE HQ-I |  | ORD/000026/2023-2024 | 109/SWD-I | 11/04/2023 | 05/02/2024 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 533.56 | 134.97 | 25.3 | 25
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Construction of Boundary Wall, Pathway, Drain, Development of Land & other allied works of SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13787). |  |  | ORD/000266/2024-2025 | 2681/SWD-I | 07/06/2024 | 22/07/2024 | M/S SHIBAM ENTERPRISE | 47.6 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00162/2024-2025 | BP-2024-25-50 | 10/05/2024 | 10/05/2024 | WBSEDCL | 13.04 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13787) |  |  | ORD/000747/2024-2025 | 4669/SWD-I | 18/11/2024 | 02/01/2025 | R.G ENTERPRISE | 10.02 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR SAMUKPOTA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016319) | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block,JE-3 | ORD/000347/2022-2023 | 2167/SWD_I | 09/12/2022 | 16/02/2025 | PADMA ENGINEERING CO. | 30.07 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SAMUKPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13787 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAMUKPOTA PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13787] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000768/2022-2023 | 3642/SWD-I | 28/03/2023 | 16/02/2025 | PADMA ENGINEERING CO. | 3.14 | 0 | 0 | 50
Total | [13 empty] | 729.11 | 134.97 | 18.51