## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BEJEORANCHA PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13917] | AE BSD |  | ORD/000577/2022-2023 | 3070/SWD-I | 21/02/2023 | 23/03/2023 | SWASTIK CONSTRUCTION (E-MAIL ID- SIDDHARTHA1978SAMADDER@GMAIL.COM) | 15.46 | 0 | 0 | 80
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Bejerancha Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000949/2022-2023 | 1280/SWD-I | 13/09/2022 | 13/10/2022 | GEO SOLUTION | 2.44 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 4.04 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BEJEORANCHA PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13917] | AE BSD | JE-1 | ORD/000300/2024-2025 | 3182/SWD-I | 15/07/2024 | 30/07/2024 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.46 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Construction of Pump house cum Chlorine room (One no.) at 1st Tube well site of BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [For T/W site-1] (SM/13917) | AE BSD | JE-1 | ORD/000660/2024-2025 | 4390/SWD-I | 23/10/2024 | 22/12/2024 | RAJ ENTERPRISE | 4.92 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at BEJEORANCHA of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 620] | AE BSD | JE-1 | ORD/000740/2022-2023 | 3593/SWD-I | 23/03/2023 | 07/12/2025 | AQUATECH ENGINEERS | 108.64 | 0 | 0 | 85
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/13917) [3rd call] |  |  | ORD/001139/2024-2025 | 242/SWD-I | 22/01/2025 | 08/03/2025 | R.K ENTERPRISE | 23.83 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bejeorancha W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13917) | Assistant Engineer | Junior Engineer | ORD/002430/2024-2025 | 124/SMSD | 22/01/2025 | 06/02/2025 | SUPER SKILL | 0.91 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Bejeorancha W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13917) | Assistant Engineer | Junior Engineer | ORD/002429/2024-2025 | 123/SMSD | 22/01/2025 | 06/02/2025 | SUPER SKILL | 0.29 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I South 24 Parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 P | SM/13917 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Bejeorancha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000483/2022-2023 | 236/SMD | 24/01/2023 | 01/09/2025 | SUPER SKILL | 11.7 | 0 | 0 | 100
Total | [13 empty] | 187.69 | 0 | 0