## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Panchpara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000409/2022-2023 | 3807/SMD | 29/12/2022 | 29/03/2023 | ALPHA ENTERPRISE | 22.82 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Panchpara Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000975/2022-2023 | 1428/SWD-I | 22/09/2022 | 22/10/2022 | GEO SOLUTION | 2.76 | 2.72 | 98.68 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 07/08/2026 | S & P ENTERPRISE | 1866.59 | 0 | 0 | 8
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PANCHPARA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13919] | AE RWS, Alipore Division | JE RWS, HQ,JE3 | ORD/000573/2022-2023 | 3066/SWD-I | 21/02/2023 | 23/03/2023 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 31.79 | 31.17 | 98.04 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 30.38 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01723/2023-2024 | BP-2023-24-196 | 09/08/2023 | 09/08/2023 | WBSEDCL | 5.58 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Construction of Boundary wall Land development & Construction of service road at 2 nd Tube Well site for PANCHPARA PWSS to accommodate FHTC in within Mograhat-II Block for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of of South 24 Parganas District. (SM/13919) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000400/2024-2025 | 3689/SWD-I | 22/08/2024 | 04/04/2025 | M/S UNIQUE ENTERPRISE | 18.87 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCHPARA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/13919 | Augmentation | Construction of Boundary wall, Construction of Approach Road, Earth Filling, Drum Sheet walling for PANCHPARA Head Work Site to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Div-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/13919) [2nd call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000771/2024-2025 | 4553/SWD-I | 06/11/2024 | 30/04/2025 | KANAK GIRI | 35.53 | 0 | 0 | 70
Total | [13 empty] | 2014.31 | 33.89 | 1.68