## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I |  | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 30/01/2023 | M/S. SREEJIT ENTERPRISE | 19 | 0 | 0 | 98
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method at Dakshin Roypur PWSS of Budge Budge-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13920] | AE SWSD-I | JE-2 | ORD/000698/2022-2023 | 3501/SWD-I | 16/03/2023 | 31/03/2023 | MAHI CONSTRUCTION | 2.17 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Construction of Boundary wall for proposed Pump House Site at Dakhin Raypur Mouza of Budge Budge-II block under South 24 Parganas W/S Divn.-I, PHE Dte. [TSM/ 017296] | AE SWSD-I |  | ORD/000350/2022-2023 | 2194/SWD-I | 13/12/2022 | 27/01/2023 | MODERN CONSTRUCTION | 6.92 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Dakhin Roypur Village(JL 70) of Budge Budge-II under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/017296] | AE SWSD-I |  | ORD/000351/2022-2023 | 2195/SWD-I | 13/12/2022 | 11/02/2023 | JYOTI ENTERPRISE | 6.81 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for water supply at Dakhin Raypur W/S Scheme under South 24 Pgs W/S Division - I, PHE Dte. in the district of South 24 Parganas. [TSM/017296] | AE SWSD-I |  | ORD/000349/2022-2023 | 2165/SWD-I | 09/12/2022 | 08/01/2023 | ZINARUL ISLAM | 14.64 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Laying HDPE pipeline under Ground Water Based Piped Water Supply Scheme of Dakshin Roypur to accommodate Functional Household Tap Connection (FHTC) in Budge Budge-II block South 24 Pgns. Dist. For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns Dist. under South 24 Pgns. Water Supply Division-I, PHE Dte. (SM/13920) | AE SWSD-I |  | ORD/000662/2022-2023 | 3378/SWD-I | 10/03/2023 | 24/04/2023 | S.P. ENTERPRISE | 6.05 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Development of land at Dakdhin Roypur PWSS Tubewell site (JL No.-70, RS-352/984, LR Dag No.- 495) under Dakshin Roypur PWSS to accomodate FHTC in Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. Dist. For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Area of South 24-Pgns. Dist. (SM/13920) | AE SWSD-I |  | ORD/000744/2022-2023 | 3595/SWD-I | 23/03/2023 | 07/04/2023 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 5.05 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Dakhin Roypur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000649/2022-2023 | 764/SMD | 15/03/2023 | 13/06/2023 | M/S. S.S. ENTERPRISE | 11.7 | 0 | 0 | 55
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Pipe supporting structure with allied works under "Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District." (TSM/017296) | AE SWSD-I | JE-2 | ORD/000399/2023-2024 | 1908/SWD-I | 21/08/2023 | 20/10/2023 | SUKUMAR DEBNATH | 4.08 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Constructure of retaining Structure near Pump House under "Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District." (TSM/017296) | AE SWSD-I | JE-2 | ORD/000413/2023-2024 | 1915/SWD-I | 21/08/2023 | 20/10/2023 | SOHINI ENTERPRISE | 2.02 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 3473/SWD-I | 15/03/2023 | 15/03/2023 | Resource Division | 2.37 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01822/2022-2023 | BP-2022-23-463 | 23/03/2023 | 23/03/2023 | WBSEDCL | 1.04 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Interconnection from proposed Tubewell to existing Distribution Line with Laying of HDPE pipeline for retrofitting of distribution system of Dakhin Raypur Village & providing FHTC under SWD - I, P.H.E. Dte District South 24 Parganas. (TSM/017296) | AE SWSD-I | JE-2 | ORD/000511/2022-2023 | 2941/SWD-I | 16/02/2023 | 17/04/2023 | M/S. S.S. ENTERPRISE | 104.69 | 0 | 0 | 90
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Roypur Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000992/2022-2023 | 1532/SWD-I | 29/09/2022 | 29/10/2022 | GEO SOLUTION | 2.42 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/13920 | Augmentation | Providing pipe supporting structures for crossing gaps over newly constructed irrigation culverts with allied works for DAKSHIN RAYPUR PWSS to accommodate FHTC in Budge Budge -II block under South 24 Parganas W/S division-I, P.H.E. Dte of South 24-Pgns District for Augmentation of Surface Water Based Water Supply Scheme in the arsenic affected areas South 24-Pgns District (SM/13920) | AE SWSD-I | JE-2 | ORD/000362/2024-2025 | 3504/SWD-I | 07/08/2024 | 21/09/2024 | SUKUMAR DEBNATH | 13.33 | 0 | 0 | 50
Total | [13 empty] | 202.28 | 0 | 0