## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for DIHI NARAYANI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [SM/13921][2nd Call] | AE RWS, Alipore Division |  | ORD/000690/2022-2023 | 3479/SWD-I | 15/03/2023 | 14/04/2023 | BENGAL ENTERPRISE | 31.75 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Dihi Narayani water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000412/2022-2023 | 3810/SMD | 29/12/2022 | 29/03/2023 | JAL PRAVAHIKA PVT. LTD. | 22.29 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 630 | 19/05/2023 |  | Resource Division | 31.74 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Preparation and submission of Detailed Project Report of "DIHINARAYANI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000881/2022-2023 | 412/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.76 | 2.64 | 95.68 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DIHI NARAYANI MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1571] [TSM/014903] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000282/2023-2024 | 1566/SWD-I | 27/07/2023 | 22/05/2024 | M/S. SUMAN ENTERPRISE | 397.95 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Construction of 900mm Dia Double Row Hume Pipe Culvert for DIHI NARAYANI PWSS to accommodate FHTC under Mograhat-II Block in the District of South 24 Parganas for Augmentation of Surfacc Water Based Water Supply Scheme under South 24-Pgns. W/S Division-I, PHE Dte. (SM/13921) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000813/2023-2024 | 1149/SWD-I | 07/03/2024 | 06/04/2024 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 5.77 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DIHI NARAYANI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affe | SM/13921 | Augmentation | Construction of Platform for providing FHTC for Ground water based DIHI NARAYANI piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13921) |  |  | ORD/000315/2024-2025 | 3248/SWD-I | 19/07/2024 | 17/09/2024 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 29.09 | 0 | 0 | 0
Total | [13 empty] | 521.34 | 2.64 | 0.51