## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Preparation and submission of Detailed Project Report of KARIMPUR KISMAT AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000419/2021-2022 | 1969/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.55 | 2.51 | 98.47 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 4.82 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03756/2023-2024 | BP-2023-24-394 | 29/11/2023 | 29/11/2023 | WBSEDCL | 5.86 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KARIMPUR KISMAT PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016562] | AE SWSD-II | JE1 | ORD/000600/2022-2023 | 3128/SWD-I | 24/02/2023 | 26/03/2023 | MRA NIRMAN UDYOG | 15.89 | 0 | 0 | 90
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Karimpur Kismat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000516/2022-2023 | 373/SMD | 13/02/2023 | 14/05/2023 | SARKAR ELECTRICAL | 22.21 | 10.58 | 47.65 | 50
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of KARIMPUR KISMAT PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 738) [TSM/016376]. | AE SWSD-II | JE4 | ORD/000722/2022-2023 | 3565/SWD-I | 22/03/2023 | 15/01/2025 | RAJLAXMI CONSTRUCTION | 117.95 | 85.81 | 72.75 | 90
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Supply & Delivery of additional materials for PH No.-1 of Karimpur Kismat Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/13922] | Assistant Engineer -II | Junior Engineer | ORD/003014/2023-2024 | 85-AE-II-SMD | 18/01/2024 | 02/02/2024 | SARKAR ELECTRICAL | 0.26 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Miscellaneous renovation works regarding outdoor illumination, LED Board etc. at P.H. No. 1 under Karimpur Kismat Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/13922) | Assistant Engineer -II | Junior Engineer | ORD/002454/2023-2024 | 222-AE-II-SMD | 01/03/2024 | 16/03/2024 | PS & ASSOCIATES | 0.75 | 0.75 | 100 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 19/03/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for KARIMPUR KISMAT Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13922] | AE SWSD-II | JE4 | ORD/000690/2024-2025 | 4485/SWD-I | 30/10/2024 | 02/02/2025 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0 | 95
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Payment of quotation for new service connection at Karimpur Kismat PWSS, PH No-2 under Bishnupur-I Block. Application No- 1008268332 Reference Id- 106861473 Quotation Date-12/12/2024 Memo No- 1008268332/Quot/03 |  |  | BILL/02489/2024-2025 | BP-2024-25-536 | 24/01/2025 | 24/01/2025 | WBSEDCL | 7.8 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KARIMPUR KISMAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Af | SM/13922 | Augmentation | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Karimpur Kismat PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns district. (SM/13922) | AE SWSD-II | JE4 | ORD/000257/2024-2025 | 2674/SWD-I | 07/06/2024 | 26/01/2026 | RAJLAXMI CONSTRUCTION | 49.25 | 11.18 | 22.7 | 75
Total | [13 empty] | 348.53 | 110.83 | 31.8