## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Khakurdaha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000581/2022-2023 | 616/SMD | 02/03/2023 | 31/05/2023 | ROY & BISWAS ENGG. CO. | 22.36 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Preparation and submission of Detailed Project Report of "KHAKURDAHA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD |  | ORD/000754/2022-2023 | 711/SWD-I | 23/06/2022 | 08/07/2022 | ECO CARE | 2.83 | 2.63 | 92.94 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 338/SWD-I | 26/04/2023 | 26/04/2023 | Resource Division | 45.83 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for KHAKURDAHA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017164] | AE BSD | JE-1 | ORD/000620/2022-2023 | 3244/SWD-I | 01/03/2023 | 31/03/2023 | MATRI ENTERPRISE | 31.75 | 15.05 | 47.41 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. |  |  | BILL/00668/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD | JE RWS | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 30/07/2025 | GARAI INFRA PROJECT | 1193.4 | 212.9 | 17.84 | 96
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KHAKURDAHA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13923 | Augmentation | Development of land, Construction of approach road and other allied works for Ground Water Based KHAKURDAHA Piped Water Supply Scheme to Accommodate FHTC in JAYNAGAR-I Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/13923) | AE BSD | JE RWS | ORD/000407/2024-2025 | 3685/SWD-I | 22/08/2024 | 14/06/2025 | GARAI INFRA PROJECT | 56.45 | 5.87 | 10.39 | 25
Total | [13 empty] | 1355.96 | 236.46 | 17.44