## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Preparation and submission of Detailed Project Report of "HANSURI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000893/2022-2023 | 403/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 2.63 | 93.15 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for HANSURI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [SM/13985][2nd Call] | AE SWSD-II | JE3 | ORD/000684/2022-2023 | 3483/SWD-I | 15/03/2023 | 14/04/2023 | K.P.D. & SONS. | 31.76 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Construction of 300 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of HANSURI MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2556] [TSM/015218] | AE S24D1,AE SWSD-II | JE3 | ORD/000050/2023-2024 | 269/SWD-I | 24/04/2023 | 01/02/2025 | TUMPA ASSOCIATES | 427.98 | 26.72 | 6.24 | 55
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Hansuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 773/SMD | 16/03/2023 | 14/06/2023 | JAL PRAVAHIKA PVT. LTD. | 22.36 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 629 | 19/05/2023 | 19/05/2023 | Resource Division | 25.67 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [WB04G4525] [SM/13985] [w.e.f. 01/12/2024 to 31/05/2025] | AE S24D1 | JE-2 | ORD/001110/2024-2025 | 4874/SWD-I | 28/11/2024 | 29/05/2025 | AJAY KUMAR | 0.86 | 1.92 | 221.97 | 11
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. | AE S24D1 | JE3 | ORD/000743/2024-2025 | 4641/SWD-I | 14/11/2024 | 12/02/2025 | M/S ESSENCE J.V. CONSTRUCTION CO. | 263.03 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [WB04G4525] [SM/13985] [w.e.f. 01/06/2025 to 30/11/2025] | AE S24D1,AE SWSD-II | JE-2 | ORD/000119/2025-2026 | 1436/SWD-I | 28/05/2025 | 27/11/2025 | AJAY KUMAR | 0.87 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/13985 | Augmentation | Quotation for new service connection at P.H. No.1 of Hansuri w/s scheme . Application no.1008079139. |  |  | BILL/02410/2024-2025 | BP-2024-25-522 | 10/01/2025 | 10/01/2025 | WBSEDCL | 5.52 | 0 | 0 | 0
Total | [13 empty] | 780.87 | 31.28 | 4.01