## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Construction of boundary wall along with humepipe culvert bridge for the approch road of proposed OHR Site at Nayapukuria Mouza, JL No.43, Khatian No. 1079, Plot No. 661 & 662; within Joynagar-II block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 180.0 mtr.] | AE BSD |  | ORD/000378/2021-2022 | 1581/SWD-I | 27/12/2021 | 27/03/2022 | SANKAR HALDER | 33.44 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 76.87 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000299/2023-2024 | 2438/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 132.42 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Raidighi River in between nodes 12 & 13 of Secondary Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/14140) |  |  | ORD/000775/2024-2025 | 4761/SWD-I | 21/11/2024 | 21/12/2024 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 139.05 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for MATHURAPUR-I Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] |  |  | ORD/000653/2024-2025 | 4376/SWD-I | 22/10/2024 | 20/01/2025 | A.P POWER AND CONCRETE | 15.66 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Supply of G.I. Pipe, Collapsible Gate, Laying of 100 mm thick interlocking design concrete paver block (M-15) grade for Mathurapur-I GLR in connection with Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.-South 24-Parganas under Baruipur Sub-Division of SWD-I, PHE Dte. (SM/14140) | AE BSD | JE-1 | ORD/000760/2024-2025 | 4681/SWD-I | 18/11/2024 | 18/12/2024 | DIAMOND ENTERPRISE | 9.4 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Balance work for application of protective coating on M.S pipe for Railway crossing at Dakshin Bishnupur Rail gate under Mega Surface water Based Water Supply Scheme for Falta-Mathurapur, Dist. South24-Pgns. of South 24-Pgs. Water Supply Divn.-I, PHE Dte. [SM/14140] | AE BSD | JE-1 | ORD/000756/2024-2025 | 4677/SWD-I | 18/11/2024 | 03/12/2024 | DIAMOND ENTERPRISE | 3.81 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. |  |  | BILL/00666/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. |  |  | BILL/00656/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD | JE-2 | ORD/000654/2024-2025 | 4377/SWD-I | 22/10/2024 | 20/01/2025 | BISWAS CONSTRUCTION | 15.58 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Providing support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instrument like Remotely Piloted Aircraft System / DGPS/ Total station etc. and detailed design of pipeline by using watergems Software on the besis of the population density within the zone-I of Joynagar-II block under Mega Surface water based water supply scheme for Falta-Mathurapur, Dist- South 24-Pgns. | AE BSD | JE-1 | ORD/000773/2020-2021 | 1038/SWD-I | 05/10/2020 | 19/10/2020 | DEVELOPMENT CONSULTANTS PVT LTD | 4.75 | 0 | 0 | 100
Total | [13 empty] | 446.13 | 0 | 0