## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Providing support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instrument like Remotely Piloted Aircraft System / DGPS/ Total station etc. and detailed design of pipeline by using watergems Software on the besis of the population density within the zone-I of Joynagar-II block under Mega Surface water based water supply scheme for Falta-Mathurapur, Dist- South 24-Pgns. | AE BSD | JE-1 | ORD/000773/2020-2021 | 1038/SWD-I | 05/10/2020 | 19/10/2020 | DEVELOPMENT CONSULTANTS PVT LTD | 4.75 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Construction of boundary wall along with humepipe culvert bridge for the approch road of proposed OHR Site at Nayapukuria Mouza, JL No.43, Khatian No. 1079, Plot No. 661 & 662; within Joynagar-II block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 180.0 mtr.] | AE BSD |  | ORD/000378/2021-2022 | 1581/SWD-I | 27/12/2021 | 27/03/2022 | SANKAR HALDER | 33.44 | 31.65 | 94.65 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I NAYAPUKURIA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 10830] [TSM/015333 & TSM/011546] | AE BSD | JE RWS | ORD/000568/2023-2024 | 2650/SWD-I | 27/10/2023 | 18/04/2026 | M/S GHOSH AND CO. | 1544.66 | 214.33 | 13.88 | 80
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 76.87 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000299/2023-2024 | 2438/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 132.42 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Additional work for Laying Distribution System of ZONE-I at JOYNAGAR-II Block, for implementation of JJM under Augmentation of Surface Based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas district. under Baruipur Sub-Division of South 24 pgns. W/S Division -I P.H.E Dte. (SM/14140) | AE BSD | JE RWS | ORD/000727/2024-2025 | 4614/SWD-I | 13/11/2024 | 14/09/2025 | MILAN GHOSH | 478.06 | 0 | 0 | 60
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Raidighi River in between nodes 12 & 13 of Secondary Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/14140) |  |  | ORD/000775/2024-2025 | 4761/SWD-I | 21/11/2024 | 21/12/2024 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 139.05 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for MATHURAPUR-I Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] |  |  | ORD/000653/2024-2025 | 4376/SWD-I | 22/10/2024 | 20/01/2025 | A.P POWER AND CONCRETE | 15.66 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD | JE-2 | ORD/000654/2024-2025 | 4377/SWD-I | 22/10/2024 | 20/01/2025 | BISWAS CONSTRUCTION | 15.58 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Supply of G.I. Pipe, Collapsible Gate, Laying of 100 mm thick interlocking design concrete paver block (M-15) grade for Mathurapur-I GLR in connection with Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.-South 24-Parganas under Baruipur Sub-Division of SWD-I, PHE Dte. (SM/14140) | AE BSD | JE-1 | ORD/000760/2024-2025 | 4681/SWD-I | 18/11/2024 | 18/12/2024 | DIAMOND ENTERPRISE | 9.4 | 9.39 | 99.97 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Balance work for application of protective coating on M.S pipe for Railway crossing at Dakshin Bishnupur Rail gate under Mega Surface water Based Water Supply Scheme for Falta-Mathurapur, Dist. South24-Pgns. of South 24-Pgs. Water Supply Divn.-I, PHE Dte. [SM/14140] | AE BSD | JE-1 | ORD/000756/2024-2025 | 4677/SWD-I | 18/11/2024 | 03/12/2024 | DIAMOND ENTERPRISE | 3.81 | 3.8 | 99.72 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. |  |  | BILL/00656/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. |  |  | BILL/00666/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Construction of RCC pathway, Masonry surface drain and other allied works inside GLR-9 under Mega Surface project in connection with Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD | JE-1 | ORD/001175/2024-2025 | 464/SWD-I | 12/02/2025 | 29/03/2025 | MILAN GHOSH | 46.62 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PH | SM/14140 | Augmentation | Supply and delivery of different dia sluice valves at Joynagar-II Block for Secondary Grid under Augmentation of laying distribution system to extend the benefit of 100% househod in Zone-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur South 24 pgns. District under South 24 pgns Water Supply Division-I, PHE Dte. (SM 14140) | AE BSD | JE-1 | ORD/000101/2025-2026 | 1814/SWD-I | 07/07/2025 | 05/09/2025 | SSPR VALVE MANUFACTURING PVT LTD | 10.7 | 0 | 0 | 100
Total | [13 empty] | 2526.17 | 259.17 | 10.26