## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site (Dag No. 893, 894, 895 & 896/1231, Khatian No. 2422, JL. No. 124, Mouza- Chandpur) & 2nd Tubewell site (Dag No. 12, Khatian No. 359, JL No. 126, Mouza- Srirampur), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/010665] | AE HQ-I | JE-4 | ORD/000458/2022-2023 | 2749/SWD-I | 27/01/2023 | 26/02/2023 | ABUTALEB MONDAL | 28.51 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000439/2022-2023 | 229/SMD | 24/01/2023 | 24/04/2023 | WEST BENGAL ENGINEERING CO. | 22.37 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDPUR PWSS at headwork site (Dag No. 893, 894, 895 & 896/1231, Khatian No. 2422, JL. No. 124, Mouza- Chandpur) & 2nd Tube-well site (Dag No. 12 Khatian No. 359, JL No. 126, Mouza- Srirampur) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010665] | AE HQ-I |  | ORD/000741/2022-2023 | 3569/SWD-I | 22/03/2023 | 06/04/2023 | ABUTALEB MONDAL | 3.13 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Construction of 300 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Chandpur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2810] | AE HQ-I | JE-4 | ORD/000085/2023-2024 | 419/SWD-I | 02/05/2023 | 26/02/2024 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 581.79 | 281.58 | 48.4 | 50
5 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/04/2023 to 30/09/2023] |  |  | ORD/000878/2022-2023 | 3730/SWD-I | 31/03/2023 | 30/09/2023 | AJAY KUMAR | 0.89 | 2.35 | 265.16 | 60
6 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/10/2023 to 31/03/2024] | AE HQ-II | JE-2 | ORD/000663/2023-2024 | 2387/SWD-I | 27/09/2023 | 28/03/2024 | AJAY KUMAR | 0.89 | 2.11 | 237.2 | 30
7 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 14.98 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 17.31 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Sinking of big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site under Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [SM/14419] |  |  | ORD/000783/2023-2024 | 853/SWD-I | 19/02/2024 | 05/03/2024 | M/S SABITA ENTERPRISE | 15.84 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/04/2024 to 30/09/2024] [Vehicle No- WB-09-1725] | AE HQ-II | JE-2 | ORD/000914/2023-2024 | 1496/SWD-I | 30/03/2024 | 29/09/2024 | AJAY KUMAR | 0.89 | 2.37 | 267.12 | 0
11 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Construction of Boundary Wall and others allied works at HW site of CHANDPUR PWSS within Bhangar-I Block CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/14419). |  |  | ORD/000556/2024-2025 | 4229/SWD-I | 30/09/2024 | 29/11/2024 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 96.12 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Sinking of big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site under Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [SM/14419] | AE HQ-I | JE-4 | ORD/000259/2024-2025 | 2801/SWD-I | 18/06/2024 | 12/06/2025 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/14419 | New | Construction of Boundary Wall and others allied works at 2nd Tubewell site of CHANDPUR PWSS within Bhangar-I Block "CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14419) (2nd call) |  |  | ORD/001149/2024-2025 | 334/SWD-I | 29/01/2025 | 15/03/2025 | MAHABUB RAHAMAN LASKAR | 11.37 | 0 | 0 | 0
Total | [13 empty] | 809.97 | 288.41 | 35.61