## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 21.97 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000245/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 17.51 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for BADI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014173] | AE HQ-I | JE-4 | ORD/000625/2022-2023 | 3238/SWD-I | 01/03/2023 | 31/03/2023 | SETABUR RAHAMAN | 31.67 | 0 | 0 | 50
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of BADI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/14487] |  |  | ORD/000557/2024-2025 | 4230/SWD-I | 30/09/2024 | 29/11/2024 | SAMSUL ENTERPRISE | 81.96 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BADI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14487] |  |  | ORD/000572/2024-2025 | 4271/SWD-I | 01/10/2024 | 31/10/2024 | PRANTIK DRILLING AGENCY | 15.9 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.41] |  |  | BILL/00471/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 26.07 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Bodra - Champahati Road, from 2.30km to 4.50km(R/S) and 6.00 km to 11.00km (R/S) [ Total Length =7200.00m] . Restoration work damaged during laying of PHE pipe line under Bodra Pipe Line Prpject under South 24 Parganas Highway Division in the District of South 24 Parganas SM/14487 |  |  | BILL/00643/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 45.04 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Quotation for new service(power) connection at Badi PH-1 Water supply scheme under Bhangar-I Block Reference ID- 106550932, Application No- 1007657894 |  |  | BILL/00567/2024-2025 | BP-2024-25-140 | 03/07/2024 | 03/07/2024 | WBSEDCL | 7.9 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Badi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000505/2022-2023 | 330/SMD | 07/02/2023 | 31/03/2025 | NITESH MANAGEMENT | 25.8 | 0 | 0 | 40
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for BADI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2842] (TSM/014173) | AE HQ-I | JE-4 | ORD/000499/2023-2024 | 2175/SWD-I | 05/09/2023 | 31/03/2025 | SAMSUL ENTERPRISE | 511.61 | 0 | 0 | 35
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | BADI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14487 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Badi PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/14487) | Assistant Engineer | Junior Engineer | ORD/001614/2024-2025 | 1543/SMSD | 25/11/2024 | 10/12/2024 | NITESH MANAGEMENT | 0.9 | 0 | 0 | 0
Total | [13 empty] | 786.32 | 0 | 0