## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Suport Agency (ISA) for implementation of community mobilization and capacity building activities under Jal jeevan Mission (JJM) support Activities for 10 blocks under South 24 Pgns W/S Div-I. | SM/14489 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the South 24 Pgs District. |  | Junior Engineer | ORD/000791/2022-2023 | 445/RS | 02/02/2023 | 02/02/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 198.37 | 49.59 | 25 | 75
2 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Suport Agency (ISA) for implementation of community mobilization and capacity building activities under Jal jeevan Mission (JJM) support Activities for 10 blocks under South 24 Pgns W/S Div-I. | SM/14489 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the South 24 Pgs District. | Assistant Engineer | Junior Engineer | ORD/000309/2023-2024 | 354/RS | 02/02/2024 | 02/08/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 122.99 | 103.2 | 83.91 | 50
Total | [13 empty] | 321.37 | 152.79 | 47.54