## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Construction of 03 (three) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for KANNYANAGAR, BAGI & BHANDARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018432, TSM/017332, TSM/017323] | AE SWSD-II | JE1,JE4 | ORD/000422/2023-2024 | 1969/SWD-I | 24/08/2023 | 19/06/2024 | H. T. R. CONSTRUCTION | 572.68 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Bagi Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000959/2022-2023 | 1138/SWD-I | 25/08/2022 | 24/09/2022 | GEO SOLUTION | 3.16 | 3.14 | 99.26 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 70.75 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at second & third Tubewell Site for BAGI PWSS of Bishnupur-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017322] | AE SWSD-II | JE4 | ORD/000548/2022-2023 | 3038/SWD-I | 20/02/2023 | 22/03/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of BAGI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4890) [TSM/017322]. | AE SWSD-II | JE4 | ORD/000159/2023-2024 | 841/SWD-I | 05/06/2023 | 03/09/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 749.97 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of BAGI PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/017322] (2nd call) | AE SWSD-II | JE4 | ORD/000237/2023-2024 | 1420/SWD-I | 17/07/2023 | 15/09/2023 | MS KRISHNA MONDAL | 18.75 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Bagi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000514/2022-2023 | 371/SMD | 13/02/2023 | 01/01/2026 | SWAPAN ENTERPRISE | 33.33 | 0 | 0 | 10
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, approach road and land development for BAGI PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/14547) | AE SWSD-II | JE4 | ORD/000346/2024-2025 | 3345/SWD-I | 25/07/2024 | 23/09/2024 | M/S B.N. ENTERPRISES | 201.23 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Additional laying of pipeline for distribution system due to revision of Laying Distribution System drawing for providing Functional Household Tap Connection (FHTC) for Proposed BAGI PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24 Pgs W/S Sub-Division-I, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (SM/14547) |  |  | ORD/000016/2025-2026 | 968/SWD-I | 09/04/2025 | 24/05/2025 | RAJLAXMI CONSTRUCTION | 43.03 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BAGI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of Sout | SM/14547 | Augmentation | Construction of 02 nos. (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement (as per Deptt. drawing) for 2nd and 3rd Tubewell sites of BAGI Pipe Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24 Parganas district, South 24 Pgns WS Division-I, P.H.E Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. (SM/14547) | AE SWSD-II | JE4 | ORD/001147/2024-2025 | 328/SWD-I | 29/01/2025 | 30/03/2025 | ROYAL CONSTRUCTION | 11.52 | 0 | 0 | 0
Total | [13 empty] | 1736.21 | 3.14 | 0.18