## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 3388/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 20.98 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 28.59 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Development of land, Construction of Boundary wall (length = 133.54m) & Construction of Approach Road (length = 30.00m) at OHR site (1st Tube well Site) for JUGDIA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14549) |  |  | ORD/000369/2024-2025 | 3508/SWD-I | 07/08/2024 | 21/09/2024 | TIYASHA ENTERPRISE | 0 | 0 | NAN | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Jugdia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 3811/SMD | 29/12/2022 | 28/06/2023 | SINHA ELECTRICALS | 33.56 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (TSM/016726) [w.e.f. 25/08/2023 to 23/02/2024] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000665/2023-2024 | 1958/SWD-I | 24/08/2023 | 23/02/2024 | AJAY KUMAR | 0.87 | 2.1 | 241.14 | 60
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 24/02/2024 to 24/08/2024] [Vehicle No:- WB-04-F-9231] | AE RWS, Alipore Division | JE RWS, HQ,JE, RWS, DH-II | ORD/000811/2023-2024 | 854/SWD-I | 19/02/2024 | 20/08/2024 | AJAY KUMAR | 0.87 | 2.09 | 240.07 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Development of land, Construction of Boundary wall (length = 133.54m) & Construction of Approach Road (length = 30.00m) at OHR site (1st Tube well Site) for JUGDIA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14549) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000379/2024-2025 | 3571/SWD-I | 12/08/2024 | 26/09/2024 | TIYASHA ENTERPRISE | 26.83 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JUGDIA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016726] (2nd Call) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000118/2023-2024 | 530/SWD-I | 11/05/2023 | 31/10/2024 | SHANTI CONSTRUCTION | 47.45 | 29.67 | 62.53 | 90
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Jugdia Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000983/2022-2023 | 1457/SWD-I | 26/09/2022 | 26/10/2022 | GEO SOLUTION | 2.77 | 2.73 | 98.44 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Construction of 500 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (3 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of JUGDIA Mouza of MOGRAHAT-II Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 3406) [TSM/016726] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000081/2023-2024 | 415/SWD-I | 02/05/2023 | 01/05/2025 | ROSENBLUTH CONSTRUCTION PRIVATE LIMITED | 621.42 | 0 | 0 | 45
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 25/08/2024 to 31/01/2025] [Vehicle No:- WB-04-F-9231] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000428/2024-2025 | 3700/SWD-I | 22/08/2024 | 29/01/2025 | AJAY KUMAR | 0.76 | 2.01 | 264.33 | 40
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 01/02/2025 to 31/07/2025] [Vehicle No:- WB-04-F-9231] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/001178/2024-2025 | 299/SWD-I | 27/01/2025 | 27/07/2025 | AJAY KUMAR | 0.86 | 1.92 | 223.47 | 19
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Additional Laying of pipeline for distribution system for Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14549) |  |  | ORD/000102/2025-2026 | 1815/SWD-I | 07/07/2025 | 05/09/2025 | RAJLAXMI CONSTRUCTION | 40.58 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14549 | Augmentation | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 01/08/2025 to 31/01/2026] [Vehicle No:- WB-04-F-9231] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000120/2025-2026 | 1941/SWD-I | 23/07/2025 | 23/01/2026 | AJAY KUMAR | 0.87 | 0 | 0 | 17
Total | [13 empty] | 826.41 | 40.52 | 4.9