## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Shyampur (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000419/2022-2023 | 3815/SMD | 29/12/2022 | 29/03/2023 | M.S.ENTERPRISE | 34.23 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 37.72 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 16/10/2025 | S & P ENTERPRISE | 1745.38 | 0 | 0 | 6
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Development of land by filling of silver sand at the head work site for proposed "Ground water waste SHYAMPUR PART-II piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District under South 24-Pgns, Water Supply Division-I, P.H.E. Dte. (SM/14550) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000672/2024-2025 | 4398/SWD-I | 23/10/2024 | 01/01/2025 | LASKAR CONSTRUCTION | 13.42 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Shyampur(part-II) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000973/2022-2023 | 1426/SWD-I | 22/09/2022 | 22/10/2022 | GEO SOLUTION | 2.73 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Construction of boundary wall, approach pathway for SHYAMPUR PART- II PWSS to accommodate FHTC in Magrahat-II block under South 24-Pgns W/S Division-I, P.H.E. Dte for Augmentation of Surface Water Based Water Supply Scheme in the arsenic affected areas of South 24-Pgns District (SM/14550) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000381/2024-2025 | 3572/SWD-I | 12/08/2024 | 23/06/2025 | SWATHI ENTERPRISE | 30.64 | 0 | 0 | 75
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Construction of Boundary wall, service road and land development at 2nd and 3rd Tubewell Site for SHYAMPUR PART-II PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14550) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000031/2025-2026 | 982/SWD-I | 09/04/2025 | 24/05/2025 | M/S MJA ENTERPRISE | 15.4 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SHYAMPUR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14550 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method for SHYAMPUR (Part-II) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/14550] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000808/2023-2024 | 1288/SWD-I | 15/03/2024 | 01/04/2025 | B.K.ENTERPRISE | 57.32 | 0 | 0 | 85
Total | [13 empty] | 1936.85 | 0 | 0