## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 3391/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 22.83 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 60.07 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (3 Nos.) for Augmentation of UTTAR GOPINATHPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 3706) [TSM/017505] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000101/2023-2024 | 471/SWD-I | 04/05/2023 | 02/08/2023 | H. ENTERPRISE | 523.07 | 456.89 | 87.35 | 92
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Additional Laying distribution system for UTTAR GOPINATHPUR PWSS to accommodate FHTC in MOGRAHAT-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas. (SM/14551) |  |  | ORD/000415/2024-2025 | 3731/SWD-I | 27/08/2024 | 11/10/2024 | AVIK ENTERPRISE | 90.2 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Land development of 2nd Tubewell site for the proposed ground water based UTTAR GOPINATHPUR Piped Water Supply Scheme to accommodate FHTC in Mograhat-II Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14551) |  |  | ORD/000839/2023-2024 | 1254/SWD-I | 13/03/2024 | 28/03/2024 | HASIBA ENTERPRISE | 1.02 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Uttar Gopinathpur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | Assistant Engineer | Junior Engineer | ORD/002780/2023-2024 | 115/SMSD | 25/01/2024 | 09/02/2024 | ASHUTOSH DAS & CO. | 0.62 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Uttar Gopinathpur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | Assistant Engineer | Junior Engineer | ORD/002781/2023-2024 | 116/SMSD | 25/01/2024 | 09/02/2024 | ASHUTOSH DAS & CO. | 0.62 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Construction of 02 (two) nos. Boundary walls (48.00mtr each) & Construction of approach Roads at TW-2 & TW-3 sites for UTTAR GOPINATHPUR PWSS to accommodate FHTC in Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14551) |  |  | ORD/000311/2024-2025 | 3223/SWD-I | 18/07/2024 | 17/08/2024 | PADMA ENGINEERING CO. | 17.61 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Gopinathpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000976/2022-2023 | 1429/SWD-I | 22/09/2022 | 22/10/2022 | GEO SOLUTION | 2.78 | 2.78 | 99.78 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05028/2023-2024 | BP-2023-24-565 | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.68 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Quotation for new service connection at P.H. NO. 2 of Uttargopinathpur w/s scheme . Application no. 1007730441. |  |  | BILL/00533/2024-2025 | BP-2024-25-131 | 24/06/2024 | 24/06/2024 | WBSEDCL | 7.15 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR GOPINATHPUR PWSS of MOGRAHAT-II block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017505] [2nd Call] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000683/2022-2023 | 3487/SWD-I | 15/03/2023 | 01/09/2025 | SHAH ENTERPRISE | 47.64 | 30.97 | 65.01 | 76
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based UTTAR GOPINATHPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic | SM/14551 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Uttar Gopinathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000420/2022-2023 | 3816/SMD | 29/12/2022 | 01/04/2025 | ASHUTOSH DAS & CO. | 33.54 | 10.27 | 30.63 | 30
Total | [13 empty] | 807.83 | 500.92 | 62.01