## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 60.24 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000311/2023-2024 | 2737/SWD-I | 06/11/2023 | 06/11/2023 | Resource Division | 18.95 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Harisankarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/003028/2022-2023 | 362/SMD | 10/02/2023 | 11/05/2023 | CINZANO | 33.51 | 10.04 | 29.96 | 30
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Harisankarpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000984/2022-2023 | 1477/SWD-I | 27/09/2022 | 27/10/2022 | MEASURE LAND | 2.76 | 2.72 | 98.54 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Restoration of Road edge and Hard shoulder damaged due to laying of pipes by PHE Dte. of Dakshin Barasat Mograhat Usthi Road from 0.00 kmp to 21.0 kmp in different stretched of Diamond Harbour Highway Sub-Division under Diamond Harbour Highway Division in the district of South 24 Parganas |  |  | BILL/00653/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 20.8 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Road restoration of Harishankarpur Bharat Ghosh more to Dakshin Mukundapur Under Magrahal II PS |  |  | BILL/01668/2024-2025 | BP-2024-25-775 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.36 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 11/10/2025 | S & P ENTERPRISE | 1866.59 | 161.9 | 8.67 | 8
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Additional estimate for construction of approach road inside of the Head work site for existing HARISANKARPUR PWSS under MAGRAHAT-II Block, South 24 Parganas Distnct for Augmentation of surfacc water based water supply scheme in the Arsenic affected areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/14643) | AE RWS, Alipore Division | JE RWS, HQ | ORD/001078/2024-2025 | 5346/SWD-I | 30/12/2024 | 14/01/2025 | N & N ENTERPRISE | 3 | 0 | 0 | 60
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Renovation of approach Road inside of the head work site and construction of entrance gate for Harishankarpur PWSS to accommodate FHTC in Magrahat-II block South 24-Parganas district. for augmentation of surface water Based water Supply Scheme in the arsenic Affected areas of South 24-Parganas District. (SM/14643) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000427/2024-2025 | 3784/SWD-I | 29/08/2024 | 28/09/2024 | N & N ENTERPRISE | 6.5 | 0 | 0 | 50
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Additional Laying of Pipeline for distribution system of HARISANKARPUR piped water supply scheme to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 pgs. District. (SM/14643) |  |  | ORD/000085/2025-2026 | 1760/SWD-I | 02/07/2025 | 31/08/2025 | BAIDYA ENTERPRISE | 51.8 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell by Rotary method at Harisankarpur 2nd & 3rd Tubewell site for HARISANKARPUR Piped Water Supply Scheme of MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/14643] |  |  | ORD/000093/2025-2026 | 1768/SWD-I | 02/07/2025 | 01/08/2025 | PADMA ENGINEERING CO. | 38.27 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARISANKARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14643 | Augmentation | Additional Electro-Mechanical works for PH No-1 of Harisankarpur W/S Scheme under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003115/2023-2024 | 166/SMSD | 05/02/2024 | 01/05/2025 | CINZANO | 0.96 | 0 | 0 | 90
Total | [13 empty] | 2104.73 | 174.66 | 8.3