## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for CHAK NITAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017334] | AE SWSD-II | JE2 | ORD/000547/2022-2023 | 3037/SWD-I | 20/02/2023 | 22/03/2023 | TAPAS KUMAR GIRI | 15.9 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chaknitai water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000515/2022-2023 | 372/SMD | 13/02/2023 | 14/05/2023 | NUPUR CHANDRA HALDER | 22.36 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Chak Netai Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000078/2023-2024 | 399/SWD-I | 28/04/2023 | 28/05/2023 | GEO SOLUTION | 3.05 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Chak Netai Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000944/2022-2023 | 1127/SWD-I | 24/08/2022 | 23/09/2022 | GEO SOLUTION | 3.05 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 38.56 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAK NETAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017334] | AE SWSD-II | JE2 | ORD/000494/2022-2023 | 2855/SWD-I | 08/02/2023 | 10/03/2023 | JINAT CONSTRUCTION | 15.89 | 0 | 0 | 1
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 16/11/2025 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK NITAI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14657] | AE SWSD-II | JE2 | ORD/000696/2024-2025 | 4491/SWD-I | 30/10/2024 | 29/11/2024 | BORING HOUSE | 15.83 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Chak Nitai PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/14657) | AE SWSD-II | JE2 | ORD/000273/2024-2025 | 2923/SWD-I | 25/06/2024 | 09/08/2024 | DEY ENTERPRISE | 71.64 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of CHAK NITAI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2257). | AE SWSD-II | JE2 | ORD/000715/2022-2023 | 3550/SWD-I | 21/03/2023 | 09/12/2025 | MAA LAXMI ENTERPRISE | 288.95 | 0 | 0 | 10
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-I,AE SWSD-II | JE-2,JE1,JE2,JE3,JE4 | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 08/07/2025 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 0 | 35
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NITAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/14657 | Augmentation | Land Development work & Protection work for approach road at Headwork site of Chak Netai PWSS for pipe lines at providing 100 % Functional Household Tap Connection (FHTC) for Proposed CHAK NETAI PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. (SM/14657) | AE SWSD-II | JE2 | ORD/001125/2024-2025 | 188/SWD-I | 17/01/2025 | 15/10/2025 | SRIJON ENTERPRISE | 29.94 | 0 | 0 | 80
Total | [13 empty] | 1153.91 | 0 | 0