## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Preparation and submission of Detailed Project Report of PUNPO Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000293/2021-2022 | 1925/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.76 | 2.62 | 94.95 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 3422/SWD-I | 13/03/2023 |  | Resource Division | 10.39 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 294/SWD-I | 25/04/2023 |  | Resource Division | 32.55 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Punpo water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000580/2022-2023 | 615/SMD | 02/03/2023 | 31/05/2023 | CONCORD ENGINEERING | 19.48 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04090/2023-2024 | BP-2023-24-417 | 16/12/2023 |  | WBSEDCL | 19.28 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04090/2023-2024 | BP-2023-24-417 | 16/12/2023 |  | WBSEDCL | 19.28 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD | JE-2 | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 07/02/2024 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 0 | 0 | 15
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PUNPO piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14658 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for PUNPO PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012506] | AE BSD | JE-2 | ORD/000501/2022-2023 | 2890/SWD-I | 13/02/2023 | 15/03/2023 | IQBAL CONSTRUCTION (EMAIL ID- AANPI8149M@GMAIL.COM) | 31.77 | 7.56 | 23.8 | 50
Total | [13 empty] | 1268.47 | 10.18 | 0.8