## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 64.27 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000310/2023-2024 | 2735/SWD-I | 06/11/2023 | 06/11/2023 | Resource Division | 15.99 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Benipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000411/2022-2023 | 3809/SMD | 29/12/2022 | 29/03/2023 | ORIENTAL ENGINEERING CO. | 33.43 | 0 | 0 | 25
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Benipur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | Assistant Engineer | Junior Engineer | ORD/002824/2023-2024 | 118/SMSD | 25/01/2024 | 09/02/2024 | ORIENTAL ENGINEERING CO. | 0.62 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BENIPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017337] (2nd Call) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000093/2023-2024 | 450/SWD-I | 04/05/2023 | 02/08/2023 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 47.69 | 0 | 0 | 66
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Benipur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000985/2022-2023 | 1482/SWD-I | 27/09/2022 | 27/10/2022 | GEO SOLUTION | 2.92 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05030/2023-2024 | BP-2023-24-564 | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.47 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 11/10/2025 | S & P ENTERPRISE | 1866.59 | 0 | 0 | 8
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Construction of boundary wall, construction of service road and land development with protection work at 2nd Tubewell site for BENIPUR PWSS under Gokarnee G.P within Mograhat-II Block under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [Length - 43.0 mtr.] (SM/14659) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000684/2024-2025 | 4479/SWD-I | 30/10/2024 | 26/08/2025 | R.K ENTERPRISE | 12.01 | 0 | 0 | 75
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Construction of Boundary wall, service road & toilet for pump house at 3rd Tube well site for BENIPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [SM/14659] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000027/2025-2026 | 979/SWD-I | 09/04/2025 | 22/08/2025 | MAHABUB RAHAMAN LASKAR | 11.79 | 0 | 0 | 60
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Laying of Additional Pipeline for distribution system for BENIPUR piped water supply scheme to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 pgs. District (SM/14659) |  |  | ORD/000086/2025-2026 | 1761/SWD-I | 02/07/2025 | 16/08/2025 | AHANA ENTERPRISE | 13.36 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BENIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14659 | Augmentation | Construction of Culvert for the approach road of proposed 2nd Tube well site for "Ground water bascd BENIPUR piped watcr supply schcmc to accommodate FHTC tn MAGRAHAT-II block, South 24 Parganas District for Augmentation of Surface water based water supply scheme In the Arsenic Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE. Dte. (SM/14659) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000714/2024-2025 | 4544/SWD-I | 06/11/2024 | 05/05/2025 | SAMIR GIRI | 11.52 | 0 | 0 | 85
Total | [13 empty] | 2080.64 | 0 | 0