## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MOLLARCHAK ISHWARPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016725] | AE SWSD-II | JE4 | ORD/000626/2022-2023 | 3240/SWD-I | 01/03/2023 | 31/03/2023 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Mallarchak Ishwaripur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 3812/SMD | 29/12/2022 | 29/03/2023 | JAL PRAVAHIKA PVT. LTD. | 22.36 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 3389/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 12.09 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 629 | 19/05/2023 | 19/05/2023 | Resource Division | 27.39 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Mallarchak Ishwaripur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000995/2022-2023 | 1466\SWD-I | 27/09/2022 | 27/10/2022 | GEO SOLUTION | 2.6 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (2 Nos.) for Augmentation of MALLARCHAK ISHWARIPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 1962) [TSM/016725] | AE S24D1,AE SWSD-II | JE3,JE4 | ORD/000065/2023-2024 | 368/SWD-I | 27/04/2023 | 01/04/2025 | M/S ROY CHOWDHURY AND CO. | 290.21 | 0 | 0 | 50
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Construction of Boundary Wall for 2nd Tubewell, land development for OHR and allied works for Mallarchak Iswaripur piped water supply scheme to accomodate FHTC in Mograhat II Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14661) [2nd call] |  |  | ORD/001122/2024-2025 | 156/SWD-I | 15/01/2025 | 01/03/2025 | MAMONI ENTERPRISE | 94.94 | 0 | 0 | 0
Total | [13 empty] | 481.29 | 0 | 0