## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Marjyada water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000416/2022-2023 | 3813/SMD | 29/12/2022 | 29/03/2023 | JAL PRAVAHIKA PVT. LTD. | 23.38 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Preparation and submission of Detailed Project Report of "MARJYADA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000880/2022-2023 | 414/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 2.77 | 98 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 29.04 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Construction of Platform for providing FHTC for Ground water based MARJYADA piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14662) |  |  | ORD/000317/2024-2025 | 3250/SWD-I | 19/07/2024 | 17/09/2024 | ALOKE KUMAR SARKAR | 46.04 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MARJYADA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/015217] (2nd Call) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000119/2023-2024 | 531/SWD-I | 11/05/2023 | 04/10/2024 | SHANTI CONSTRUCTION | 47.45 | 22.69 | 47.83 | 34
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Concrete work for Repairing of Road damaged by Laying of pipe line for Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/14662) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000673/2024-2025 | 4399/SWD-I | 23/10/2024 | 22/12/2024 | ARNAB KUMAR SARKAR | 16.78 | 4.44 | 26.46 | 100
Total | [13 empty] | 165.52 | 29.9 | 18.07