## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Marjyada water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000416/2022-2023 | 3813/SMD | 29/12/2022 | 29/03/2023 | JAL PRAVAHIKA PVT. LTD. | 23.38 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Preparation and submission of Detailed Project Report of "MARJYADA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000880/2022-2023 | 414/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 2.77 | 98 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 29.04 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Construction of 900mm Dia Double Row Hume Pipe Culvert, Land Development & other allied works at OHR site under Ground water based MARJYADA PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, South 24 Pgns. District for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [SM/14662] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000820/2023-2024 | 1237/SWD-I | 12/03/2024 | 26/04/2024 | ARNAB KUMAR SARKAR | 23.69 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Construction of Platform for providing FHTC for Ground water based MARJYADA piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14662) |  |  | ORD/000317/2024-2025 | 3250/SWD-I | 19/07/2024 | 17/09/2024 | ALOKE KUMAR SARKAR | 46.04 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MARJYADA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/015217] (2nd Call) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000119/2023-2024 | 531/SWD-I | 11/05/2023 | 04/10/2024 | SHANTI CONSTRUCTION | 47.45 | 22.69 | 47.83 | 34
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Concrete work for Repairing of Road damaged by Laying of pipe line for Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/14662) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000673/2024-2025 | 4399/SWD-I | 23/10/2024 | 22/12/2024 | ARNAB KUMAR SARKAR | 16.78 | 4.44 | 26.46 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of MARYADA MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2475] [TSM/015217] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000520/2023-2024 | 2265/SWD-I | 14/09/2023 | 01/05/2025 | ALOKE KUMAR SARKAR | 506.02 | 250.02 | 49.41 | 50
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/14662 | Augmentation | Additional Laying of distribution system including construction of pipe carrying structure for Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14662) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000096/2025-2026 | 1771/SWD-I | 02/07/2025 | 16/08/2025 | ARNAB KUMAR SARKAR | 28.64 | 0 | 0 | 0
Total | [13 empty] | 723.87 | 279.93 | 38.67