## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 3390/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 20.41 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 52.85 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MULTI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [TSM/017503][2nd Call] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000686/2022-2023 | 3485/SWD-I | 15/03/2023 | 25/02/2025 | TRAYEE DECORATOR | 47.63 | 0 | 0 | 66
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Multi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000418/2022-2023 | 3814/SMD | 29/12/2022 | 29/03/2023 | S.P. CONSTRUCTION | 33.56 | 0 | 0 | 30
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Construction of Boundary wall (length = 51.00m), Development of Land at 3rd Tubewell site and Construction of Service Road (length = 25.00m) at 3rd Tubewell site for MULTI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14663) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000868/2024-2025 | 4926/SWD-I | 03/12/2024 | 01/02/2025 | M/S ASHA ENGINEERING | 12.41 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Allied Electro-Mechanical works at Pump House no-1 of Multi W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | Assistant Engineer | Junior Engineer | ORD/003008/2023-2024 | 235/SMSD | 16/02/2024 | 02/03/2024 | S.P. CONSTRUCTION | 0.41 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Multi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000978/2022-2023 | 1434/SWD-I | 23/09/2022 | 23/10/2022 | GEO SOLUTION | 2.84 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Sarberia-Dhamua Road from 0+00 to 6+520 km Restoration of Damages occurred due to damages caused/ to be caused by laying of pipe line by PHE Dte. under Sarberia PWSS,Jaldhapa PWSS,Multi PWSS under South 24 Parganas Highway Division in the district of South 24 Parganas. |  |  | BILL/00645/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 106.91 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (3 Nos.) for Augmentation of MULTI Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 3314) [TSM/017503] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000098/2023-2024 | 468/SWD-I | 04/05/2023 | 22/04/2025 | KINGS & CO. | 512.59 | 0 | 0 | 87
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Construction of Boundary wall, Box Culvert & Development of Land at TW-2 site and Construction of Service Road at OHR site & TW2 site for MULTI PWSS to accommodate FHTC within Mograhat-II Block underSouth 24-Pgns, W/S Divn-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of of South 24 Parganas District (SM/14663) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000330/2024-2025 | 3268/SWD-I | 22/07/2024 | 20/04/2025 | TIYASHA ENTERPRISE | 23.89 | 0 | 0 | 40
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MULTI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/14663 | Augmentation | Additional 60mtr. boring of Sinking of 02 (Two ) nos. (for 2nd TW a7 3rd TW) Rig bored 250mm X 150mm dia. & upto 360 mtr. deep Tubewell by Rotary method for MULTI PWSS of Mograhat-II Block under South 24-Pgns. W/S Divn.-I, PHE Dte. for Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas District. (SM/14663) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000530/2024-2025 | 4076/SWD-I | 19/09/2024 | 01/04/2025 | TRAYEE DECORATOR | 4.72 | 0 | 0 | 30
Total | [13 empty] | 818.23 | 0 | 0