## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So | SM/14724 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of JALGHARA in MOGRAHAT-I (ZONE-X/A) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II |  | ORD/000305/2021-2022 | 1982/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 3.32 | 3.01 | 90.59 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So | SM/14724 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 284/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 298.22 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So | SM/14724 | Augmentation | Construction of FHTC platform, additional pipelines of distribution system, protection of pipelines, construction of approach road and Chlorination Room under Augmentation of existing laying distribution system and new OHR and allied works to extend the benefit of 100% household in Zone-X/A at JALGHARA of Magrahat -I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under South 24 Pgns W/S Division-I. PHE Dte (SM/14724) |  |  | ORD/000442/2024-2025 | 3892/SWD-I | 04/09/2024 | 03/12/2024 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 333.65 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So | SM/14724 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of Zone-X/A (Jal Ghara) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 112 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II |  | ORD/000379/2021-2022 | 2691/SWD-I | 25/03/2022 | 23/06/2022 | MS P B CONSTRUCTION | 15.28 | 14.92 | 97.65 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/A at JALGHARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- So | SM/14724 | Augmentation | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/A AT JALGHARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/A AT JALGHARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Total Number of FHTC ¿ 9256 Nos.) | AE SWSD-II,Assistant Engineer | JE2 | ORD/000804/2022-2023 | 3695/SWD-I | 30/03/2023 | 02/04/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1210.7 | 142.51 | 11.77 | 25
Total | [13 empty] | 1861.17 | 160.44 | 8.62