## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of Zone-I (Bainchberia) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II |  | ORD/000343/2021-2022 | 2692/SWD-I | 25/03/2022 | 23/06/2022 | NIKHIL SAMADDAR | 16.45 | 16.44 | 99.91 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 284/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 3.53 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Carriage of DI (K9) pipes of various diameter from different PHE stores to work site at Mograhat-I block for laying of Secondary Grid pipeline for Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% household in Zone-I at Bainchberia under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur dist. South 24 Pgns. under South 24 Parganas Water Supply Division-I, PHE, Dte. (SM/ 14726) | AE SWSD-II | JE2,JE4 | ORD/000554/2023-2024 | 2520/SWD-I | 09/10/2023 | 16/10/2023 | TIRUPATI ENTERPRISES | 7.85 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Protection work of Boundary wall along canal inside Magrahat-I GLR under Augmentation of existing laying distribution system including old OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under Magrahat-I block within Mega Surface water based water supply scheme of Falta-Mathurapur dist- South 24-Pgns, Under south 24-Pgns, water supply Division-I, P.H.E. Dte. (SM/14726) | AE SWSD-II | JE4 | ORD/000778/2023-2024 | 806/SWD-I | 16/02/2024 | 02/03/2024 | PROJECT AND MAINTENANCE | 11.16 | 11.17 | 100.14 | 95
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Sludge cleaning including repeated washing with fresh water with allied work disinfection of Magrahat-I (1400 cum) GLRs under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in Zone-I at BAINCHBERIA under MAGRAHAT-I block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/14726) |  |  | ORD/000779/2023-2024 | 807/SWD-I | 16/02/2024 | 02/03/2024 | NIRMAL UDYOG | 3.84 | 3.64 | 94.9 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Construction of 750 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of piped water supply scheme in Zone-I at Bainchberia Mouza of Mograhat-I Block for augmentation of Mega surface water based water supply scheme and providing Functional Household Tap connection (FHTC) in Zone-I at Bainchberia of Mograhat-I Block within Mega surface water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (No.of FHTC - 5799 Nos.) | AE SWSD-II | JE3 | ORD/000114/2023-2024 | 526/SWD-I | 11/05/2023 | 01/07/2025 | RADIANT | 911.48 | 78.12 | 8.57 | 20
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Laying of additional pipe line, protection of distribution pipe line & construction of FHTC Platform, approach road, land development, chlorination room, and other allied works for Zone-I (Bainchberia) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14726] | AE SWSD-II | JE3 | ORD/000503/2024-2025 | 3719/SWD-I | 23/08/2024 | 01/07/2025 | RADIANT | 414.1 | 0 | 0 | 15
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Construction of thrust block, fabricating covers for valve chambers and supply of vent cowl, repairing leakage and construction of valve chamber for G.L.R. - IV at Usthi, Magrahat-I of Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 pgns water supply division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE4 | ORD/000763/2024-2025 | 4684/SWD-I | 18/11/2024 | 02/01/2025 | PROJECT AND MAINTENANCE | 14.36 | 3.76 | 26.2 | 95
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for Magrahat-I Block under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in Zone-I at BAINCHBERIA under Magrahat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE4 | ORD/001074/2024-2025 | 5342/SWD-I | 30/12/2024 | 30/03/2025 | TIRUPATI ENTERPRISES | 25.7 | 0 | 0 | 1
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- S | SM/14726 | Augmentation | Providing support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System / DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-I of Mograhat-I block under Mega surface water based water supply scheme for Falta-Mathurapur, Dist-South 24 pgs. | AE S24D1 | JE3 | ORD/000776/2020-2021 | 1046/SWD-I | 05/10/2020 | 01/10/2022 | DEVELOPMENT CONSULTANTS PVT LTD | 4.52 | 0 | 0 | 98
Total | [13 empty] | 1412.97 | 113.13 | 8.01