## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-V at BARIJPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- Sout | SM/14727 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000257/2023-2024 | 1718/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 188.58 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-V at BARIJPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- Sout | SM/14727 | Augmentation | Laying on distribution system at zone-V, Mograhat-I Block under 'MEGA SURFACE WTER BASED WATER SUPPLY SCHEME" for Falta-Mathurapur, Dist. South 24-Pgs. Under South 24-Pgns. W/S Divn.-I, PHE Dte. | AE SWSD-II | JE3 | ORD/000140/2022-2023 | 1359/SWD-I | 19/09/2022 | 01/04/2025 | M/S. S.S. ENTERPRISE | 511.9 | 131.02 | 25.59 | 75
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-V at BARIJPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- Sout | SM/14727 | Augmentation | Laying of additional pipe line, protection of distribution pipe line & construction of FHTC Platform, approach road, land development, chlorination room, and other allied works for Zone-V (Barijpur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14727] | AE SWSD-II | JE3 | ORD/000368/2024-2025 | 3527/SWD-I | 07/08/2024 | 07/05/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 480.15 | 0 | 0 | 40
Total | [13 empty] | 1180.63 | 131.02 | 11.1