## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/B at KALOKAPOTA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- | SM/14728 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for zone-X/B, Kalikapota (OHR Cap-600 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II |  | ORD/000309/2021-2022 | 2605/SWD-I | 15/03/2022 | 15/03/2023 | MS R. DUTTA AND CO | 2.08 | 2.08 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/B at KALOKAPOTA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- | SM/14728 | Augmentation | Construction of 600 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/B AT KALIKAPOTA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/B KALIKAPOTA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 4780 Nos.) | AE SWSD-II,Assistant Engineer | JE2 | ORD/000751/2022-2023 | 3618/SWD-I | 24/03/2023 | 18/01/2024 | TARUN ENTERPRISE | 922.07 | 345.32 | 37.45 | 70
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-X/B at KALOKAPOTA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- | SM/14728 | Augmentation | Construction of FHTC platform, additional pipelines of distribution system, protection of pipelines, upgradation of boundary wall and construction of Chlorination Roomunder Augmentation of existing laying distribution system and new OHR and allied works to extend the benefit of 100% household in Zone-X/B at KALIKAPOTA of Magrahat -I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under South 24 Pgns W/S Division-I. PHE Dte (SM/14728) |  |  | ORD/000406/2024-2025 | 3630/SWD-I | 20/08/2024 | 18/11/2024 | HUMAYUN SK. CONSTRUCTION | 209.98 | 0 | 0 | 0
Total | [13 empty] | 1134.12 | 347.4 | 30.63