## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Widening & strengthening of the approach road from the main road towards the OHR Site (From Samsuddin Mondal's house to Zone 8 OHR site) of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II |  | ORD/000341/2021-2022 | 1234/SWD-I | 12/11/2021 | 27/11/2021 | J. ENTERPRISE | 4.73 | 4.7 | 99.4 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Widening & strengthening of the approach road from the OHR Site of Zone-8 to Paschim Khelarampur F.P. School of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II |  | ORD/000342/2021-2022 | 1236/SWD-I | 12/11/2021 | 27/11/2021 | S.P. ENTERPRISE | 4.8 | 4.8 | 99.94 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of Zone-VIII (Khelarampur) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II |  | ORD/000344/2021-2022 | 2693/SWD-I | 25/03/2022 | 23/06/2022 | J. ENTERPRISE | 16.51 | 15.21 | 92.12 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Widening & strengthening of the approach road from the main road towards the OHR Site (From Sirakole road to Pranab Sardar's house) of Zone-8 of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II |  | ORD/000340/2021-2022 | 1233/SWD-I | 12/11/2021 | 27/11/2021 | J. ENTERPRISE | 4.81 | 4.76 | 98.92 | 100
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 284/SWD-I | 24/04/2023 |  | Resource Division | 3.52 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of 1450 cum capacity 20 mtr. staging heigtht Over Head Reservoir as per Departmental Drawing and specification including RCC bored pile and pile cap, Laying Distribution System of piped water supply scheme in Zone - VIII at Khelarampur Mouza of Mograhat-I Block, for augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (Number of FHTC-11274 Nos.) | AE SWSD-II | JE4 | ORD/000677/2022-2023 | 3454/SWD-I | 14/03/2023 | 08/01/2024 | M/S. S.S. ENTERPRISE | 1859.15 | 351.15 | 18.89 | 16
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of FHTC platform, road restoration and other allied works for Zone-VIII (Khelarampur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14729] |  |  | ORD/000289/2024-2025 | 3105/SWD-I | 09/07/2024 | 06/11/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 426.02 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Providing support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotely Piloted Aircraft System / DGPS / Total station etc. and detailed design of pipeline by using Watergems Software on the besis of the population density within the Zone-VIII of Mograhat-I block under Mega surface water based water supply scheme for Falta-Mathurapur, Dist- South 24-Pgns. |  |  | ORD/000771/2020-2021 | 1048/SWD-I | 05/10/2020 | 19/10/2020 | DEVELOPMENT CONSULTANTS PVT LTD | 4.84 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Land development at OHR site of KHELARAMPUR, ZONE-VIII of Mograhat-I Block for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% household in Zone-VIII at KHELARAMPUR within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/14729) | AE SWSD-II | JE4 | ORD/000429/2024-2025 | 3871/SWD-I | 03/09/2024 | 03/10/2024 | NIRMAL UDYOG | 6.87 | 0 | 0 | 0
Total | [13 empty] | 2331.26 | 380.63 | 16.33