## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Widening & strengthening of the approach road from the main road towards the OHR Site (From Samsuddin Mondal's house to Zone 8 OHR site) of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II |  | ORD/000341/2021-2022 | 1234/SWD-I | 12/11/2021 | 27/11/2021 | J. ENTERPRISE | 4.73 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Widening & strengthening of the approach road from the OHR Site of Zone-8 to Paschim Khelarampur F.P. School of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II |  | ORD/000342/2021-2022 | 1236/SWD-I | 12/11/2021 | 27/11/2021 | S.P. ENTERPRISE | 4.8 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of Zone-VIII (Khelarampur) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II |  | ORD/000344/2021-2022 | 2693/SWD-I | 25/03/2022 | 23/06/2022 | J. ENTERPRISE | 16.51 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Widening & strengthening of the approach road from the main road towards the OHR Site (From Sirakole road to Pranab Sardar's house) of Zone-8 of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II |  | ORD/000340/2021-2022 | 1233/SWD-I | 12/11/2021 | 27/11/2021 | J. ENTERPRISE | 4.81 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 284/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 3.52 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Payment for Initial 50% of Rs 18504950.00 (Rupees One Crore Eighty Five lakh Four Thousand Nine Hu8ndred Fifty only) i.e. Rs. 9252475.00 (Rupees Ninety two lakh Fifty Two Thousand Four Hundred seventy Five only) For road restoration, damaged due to laying of pipeline at Usthi Sirakol, Sirakol Amratala, Usthi Deula roads and road crossings under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (TSM/014912, SM/14729) |  |  | BILL/00593/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 92.52 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of 1450 cum capacity 20 mtr. staging heigtht Over Head Reservoir as per Departmental Drawing and specification including RCC bored pile and pile cap, Laying Distribution System of piped water supply scheme in Zone - VIII at Khelarampur Mouza of Mograhat-I Block, for augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (Number of FHTC-11274 Nos.) | AE SWSD-II | JE4 | ORD/000677/2022-2023 | 3454/SWD-I | 14/03/2023 | 01/09/2025 | M/S. S.S. ENTERPRISE | 1859.15 | 0 | 0 | 52
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of FHTC platform, road restoration and other allied works for Zone-VIII (Khelarampur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14729] | AE SWSD-II | JE4 | ORD/000289/2024-2025 | 3105/SWD-I | 09/07/2024 | 07/03/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 426.02 | 0 | 0 | 20
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist. | SM/14729 | Augmentation | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 08/06/2025 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0 | 0
Total | [13 empty] | 2431.45 | 0 | 0