## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Construction of 350 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for ATGHARA Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2247) (TSM/018118) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000049/2023-2024 | 268/SWD-I | 24/04/2023 | 18/02/2024 | TUMPA ASSOCIATES | 421.83 | 31.27 | 7.41 | 30
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Atghara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 1052/SMD | 17/04/2023 | 16/07/2023 | M.S.ENTERPRISE | 23.44 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ATGHARA PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018118] (2nd Call) | AE HQ-I |  | ORD/000224/2023-2024 | 1400/SWD-I | 14/07/2023 | 13/08/2023 | G.B. CONSTRUCTION | 31.7 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 18.93 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000243/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 13.84 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of ATGHARA PWSS within Sonarpur Block "ATGHARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14857) | Assistant engineer (contractual) | JE-3 | ORD/000230/2024-2025 | 2650/SWD-I | 07/06/2024 | 22/07/2024 | JHARNA ENTERPRISE (PROP. PINAKY KARMAKAR) | 10.83 | 9.88 | 91.19 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of Head Work Site ATGHARA PWSS within Sonarpur Block ATGHARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14857) | Assistant engineer (contractual) | JE-3 | ORD/001071/2024-2025 | 5339/SWD-I | 30/12/2024 | 10/11/2025 | RAJ CONSTRUCTION | 39.61 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ATGHARA PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018118] | AE HQ-II | JE-3 | ORD/000747/2023-2024 | 561/SWD-I | 31/01/2024 | 15/02/2024 | MUNNA AGROTECH ENTERPRISE | 15.85 | 15.53 | 97.98 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Earthwork in filling in Head Work Site with good earth for proposed ATGHARA Pipe water supply scheme to accommodate FHTC in Sonarpur Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. under Jal Jeevan Mission.(SM/14857) | Assistant engineer (contractual) | JE-3 | ORD/000742/2023-2024 | 524/SWD-I | 29/01/2024 | 24/12/2024 | SUPER CONSTRUCTION | 7.17 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | ATGHARA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/14857 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for ATGHARA PWSS of SONARPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/14857] | Assistant engineer (contractual) | JE-3 | ORD/000787/2023-2024 | 1070/SWD-I | 04/03/2024 | 08/02/2025 | BORING HOUSE | 15.81 | 0 | 0 | 100
Total | [13 empty] | 599.03 | 56.68 | 9.46