## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14858 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 295/SWD-I | 25/04/2023 |  | Resource Division | 23.39 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14858 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Banberia ( Zone-40) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000009/2023-2024 | 944/SMD | 04/04/2023 | 03/07/2023 | ORIENTAL ENGINEERING CO. | 43.1 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14858 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based BANBERIA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000923/2022-2023 | 1176/SWD-I | 31/08/2022 | 30/09/2022 | ASTER CONSULTANCY | 3.01 | 1.5 | 50 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14858 | Augmentation | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of BANBERA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2949] [TSM/018364] | AE BSD | JE RWS Baruipur Block | ORD/000158/2023-2024 | 842/SWD-I | 05/06/2023 | 03/09/2023 | RELIABLE CONSTRUCTIONS | 349.93 | 200.53 | 57.31 | 85
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BANBERA (ZONE-40) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14858 | Augmentation | Sinking of 04 (four) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BANBERA (Zone-40) Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/14858) |  |  | ORD/000445/2024-2025 | 3895/SWD-I | 04/09/2024 | 03/12/2024 | ASIT PRAMANIK | 63.43 | 0 | 0 | 0
Total | [13 empty] | 482.86 | 202.03 | 41.84