## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based HARAL Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000921/2022-2023 | 1173/SWD-I | 31/08/2022 | 30/09/2022 | ASTER CONSULTANCY | 3.08 | 3.08 | 99.87 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of HARAL MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2089] [TSM/018361] | AE BSD | JE-1 | ORD/000027/2023-2024 | 98/SWD-I | 10/04/2023 | 09/07/2023 | SAMSUL ENTERPRISE | 398.11 | 310.74 | 78.05 | 90
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Haral ( Zone-28) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 942/SMD | 04/04/2023 | 03/07/2023 | M.S.ENTERPRISE | 39.1 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 16.72 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Sinking of 03 (Three) Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at HARAL Piped Water Supply Scheme to accommodate FHTC in Baruipur Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/14859) | AE BSD | JE-1 | ORD/000443/2024-2025 | 3893/SWD-I | 04/09/2024 | 07/01/2026 | KALPANA BUILDERS (SALTLAKE) | 47.65 | 0 | 0 | 33
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based HARAL piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14859) |  |  | ORD/000229/2024-2025 | 2646/SWD-I | 07/06/2024 | 22/07/2024 | SAMSUL ENTERPRISE | 50.8 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Road restoration for Chiner More to Haral Bani Scociation Bituminaous Via Punri Katpole to Bonabibi Tala. |  |  | BILL/01695/2024-2025 | BP-2024-25-784 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.12 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Auliapur to Uttarbhag road,Permanent rsetoration work for 13000 mtr of trench (0.00 Km-5.0 Km(L/S),5.00Km-7.75 Km(B/S), 7.75 km-9.30 Km(R/S), 9.30 Km-9.55 Km(B/S) & 9.55 Km-10.0 Km) Total trench length:13000 mtr cause due to pipe laying work of PHED under South 24 Parganas Division, PWD in the district of South 24 Parganas-During the year 2024-2025. |  |  | BILL/00541/2024-2025 | BP-2024-25-332 | 24/09/2024 | 24/09/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 107.89 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARAL (ZONE-28) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/14859 | Augmentation | Construction of Pump house cum Chlorine room (Three nos.) at HARAL piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/14859) |  |  | ORD/000011/2025-2026 | 935/SWD-I | 07/04/2025 | 06/06/2025 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 13.59 | 0 | 0 | 0
Total | [13 empty] | 678.06 | 313.81 | 46.28