## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14861 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Tajpur Fatepur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 1043/SMD | 17/04/2023 | 16/07/2023 | M/S. S.S. ENTERPRISE (DOMKAL) | 22.55 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14861 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Tajpur Fatepur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000954/2022-2023 | 1305/SWD-I | 14/09/2022 | 14/10/2022 | GEO SOLUTION | 2.66 | 2.64 | 99.35 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14861 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 35.84 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14861 | Augmentation | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for TAJPUR FATEPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018300] | AE BSD | JE-1 | ORD/000613/2022-2023 | 3212/SWD-I | 28/02/2023 | 30/03/2023 | NAJMUL HAQUE | 31.62 | 0 | 0 | 5
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14861 | Augmentation | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of TAJPUR FATEPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2497] [TSM/018300] | AE BSD | JE-1 | ORD/000127/2023-2024 | 587/SWD-I | 16/05/2023 | 11/03/2024 | DIVINE | 531.16 | 187.91 | 35.38 | 25
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TAJPUR FATEPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14861 | Augmentation | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Restoration of Road, and other allied works for "Ground Water Based Tajpur Fatepur Piped Water Supply Scheme to Accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/14861) |  |  | ORD/000356/2024-2025 | 3456/SWD-I | 02/08/2024 | 16/09/2024 | DIVINE | 84.28 | 0 | 0 | 0
Total | [13 empty] | 708.12 | 190.56 | 26.91