## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based TEAUR HAT Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000918/2022-2023 | 1169/SWD-I | 30/08/2022 | 29/09/2022 | ASTER CONSULTANCY | 3.12 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 21.65 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TEURHAT MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2688] [TSM/018362] | AE BSD | JE-1 | ORD/000802/2022-2023 | 3693/SWD-I | 30/03/2023 | 28/06/2023 | PATHIK PABAN NANDI | 428.89 | 0 | 0 | 85
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Sinking of 04 (four) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TEURHAT PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/14862] |  |  | ORD/000719/2023-2024 | 362/SWD-I | 16/01/2024 | 01/03/2024 | SAIKAT ENTERPRISE | 63.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head Work site for TEURHAT (ZONE-41) PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/14862] | AE BSD | JE-1 | ORD/000299/2024-2025 | 3180/SWD-I | 15/07/2024 | 30/07/2024 | PADMA ENGINEERING CO. | 15.9 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Teurhat ( Zone-41) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 943/SMD | 04/04/2023 | 01/07/2026 | DAS ENTERPRISE | 52.78 | 0 | 0 | 40
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Construction of Pump house cum Chlorine room (Four nos.) at TEURHAT piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/14862) | AE BSD | JE-1 | ORD/000683/2024-2025 | 4478/SWD-I | 30/10/2024 | 25/09/2025 | R.K ENTERPRISE | 19.65 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of TeurhatW/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14862) | Assistant Engineer | Junior Engineer | ORD/000083/2025-2026 | 696/SMSD | 15/05/2025 | 30/05/2025 | DAS ENTERPRISE | 0.93 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-4 of TeurhatW/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14862) | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 697/SMSD | 15/05/2025 | 30/05/2025 | DAS ENTERPRISE | 0.93 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2,3 & 4 of Teurhat (Zone-41) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14862) | Assistant Engineer | Junior Engineer | ORD/001829/2024-2025 | 417/SMSD | 20/03/2025 | 04/04/2025 | DAS ENTERPRISE | 0.88 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based TEURHAT (ZONE-41) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/14862 | Augmentation | Sinking of 03 (three) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd, 3rd and 4th Tubewell sites at TEURHAT Piped Water Supply Scheme to accommodate FHTC in Baruipur block under South 24-Pgns. W/S Division-I, PHE Dte. for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/14862] | AE BSD | JE-1 | ORD/000532/2024-2025 | 4078/SWD-I | 19/09/2024 | 01/04/2025 | DEV & COMPANY | 47.69 | 0 | 0 | 100
Total | [13 empty] | 656 | 0 | 0