## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 3392/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 13.84 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 39.14 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Urel Chandpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 1047/SMD | 17/04/2023 | 16/07/2023 | SUBHRA ENTERPRISE | 22.37 | 0 | 0 | 45
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Allied Electro-Mechanical works at Pump House no-1 of Urel Chandpur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | Assistant Engineer | Junior Engineer | ORD/002782/2023-2024 | 117/SMSD | 25/01/2024 | 09/02/2024 | SUBHRA ENTERPRISE | 0.28 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Construction of Platform for providing FHTC for Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14863) |  |  | ORD/000323/2024-2025 | 3256/SWD-I | 19/07/2024 | 17/09/2024 | M/S V.P. JAIN | 41.83 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Urel Chandpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000970/2022-2023 | 1387/SWD-I | 20/09/2022 | 20/10/2022 | GEO SOLUTION | 2.7 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at UREL CHANDPUR Mouza of Mograhat-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2247] [TSM/017336] | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000063/2023-2024 | 367/SWD-I | 27/04/2023 | 16/07/2025 | M/S V.P. JAIN | 319.81 | 0 | 0 | 95
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14863 | Augmentation | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tub-ewell having 66 mtr. housing pipe by Rotary method for UREL CHANDPUR PWSS of Mograhat-II block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017336] | AE RWS, Alipore Division | JE RWS, Magrahat-II Block,JE3 | ORD/000550/2022-2023 | 3049/SWD-I | 20/02/2023 | 10/04/2025 | PADMA ENGINEERING CO. | 31.8 | 0 | 0 | 100
Total | [13 empty] | 471.77 | 0 | 0