## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Preparation and submission of Detailed Project Report of "DAKSHIN KASHI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000882/2022-2023 | 417/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.9 | 2.58 | 89.03 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for DAKSHIN KASHI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017968][2nd Call] | AE S24D1,AE SWSD-II | JE3 | ORD/000688/2022-2023 | 3477/SWD-I | 15/03/2023 | 14/04/2023 | MUNNA AGROTECH ENTERPRISE | 31.75 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DAKSHIN KASHI MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2171] [TSM/017968] | AE S24D1,AE SWSD-II | JE3 | ORD/000036/2023-2024 | 122/SWD-I | 12/04/2023 | 24/09/2026 | KUDUCH MOLYA | 388.6 | 57.4 | 14.77 | 65
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Dakshin Kashi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000052/2023-2024 | 1048/SMD | 17/04/2023 | 16/07/2023 | GOENKA ENTERPRISE | 26.03 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 629 | 19/05/2023 | 19/05/2023 | Resource Division | 22.78 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14870) | AE S24D1 | JE3 | ORD/000301/2024-2025 | 3199/SWD-I | 16/07/2024 | 01/04/2025 | KUDUCH MOLYA | 269.02 | 0 | 0 | 50
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14870 | Augmentation | Quotation for new service connection at P.H. NO.1 of Dakshin Kashi w/s scheme . Application no. 1008268486 . |  |  | BILL/02417/2024-2025 | BP-2024-25-519 | 10/01/2025 | 10/01/2025 | WBSEDCL | 11.12 | 0 | 0 | 0
Total | [13 empty] | 752.2 | 59.98 | 7.97