## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for GABBARIA PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018429] | AE SWSD-II | JE4 | ORD/000581/2022-2023 | 3095/SWD-I | 23/02/2023 | 25/03/2023 | MD RUHUL AMIN GOLDER | 15.88 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gabberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000591/2023-2024 | 2357/SMD | 30/06/2023 | 28/09/2023 | SRI KRISHNA NIRMAN | 22.37 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Gabbaria Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000966/2022-2023 | 1165/SWD-I | 29/08/2022 | 28/09/2022 | GEO SOLUTION | 2.7 | 2.7 | 100 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 67.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of GABBERIA PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2259) [TSM/018429] | AE SWSD-II | JE4 | ORD/000046/2023-2024 | 242/SWD-I | 20/04/2023 | 01/04/2026 | MONDAL PRECISION PVT. LTD. | 311.23 | 202.08 | 64.93 | 30
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Repairing and renovation of Overhead Reservoir (220 cum. Capacity) for Gabberia P.W.S.S. under South 24-Pgs. W/S Sub-Divn- II under surface water based water supply scheme in the Arsenic affected area of South 24 Pgs. Dist. [SM/14871] | AE SWSD-II | JE4 | ORD/000836/2023-2024 | 1291/SWD-I | 15/03/2024 | 29/04/2024 | S.P. ENTERPRISE | 6.38 | 6.22 | 97.58 | 96
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Construction of 200 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for GABBARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district, under South 24 Pgns Water Supply Division-1, PHE Dte. [TSM/018429] | AE SWSD-II | JE4 | ORD/000030/2023-2024 | 111/SWD-I | 11/04/2023 | 24/12/2025 | SHAKUNTALA CONSTRUCTION | 107.41 | 37.91 | 35.3 | 65
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Construction of approach road, protection work of pipeline, upgradation of existing boundary wall, laying rising mai nand other allied works for GABBARIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/14871] | AE SWSD-II | JE4 | ORD/000247/2024-2025 | 2667/SWD-I | 07/06/2024 | 01/04/2025 | SHAKUNTALA CONSTRUCTION | 82.98 | 0 | 0 | 45
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Interconnection of 2 nos. OHRs with existing 1422 mm rising main pipe for Gabberia PWSS under Bishnupur -I District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/14871) |  |  | ORD/000089/2025-2026 | 1764/SWD-I | 02/07/2025 | 01/08/2025 | S. ROY AND ASSOCIATES | 8.88 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GABBARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of | SM/14871 | Augmentation | Upgradation of Store including preparation of approach road at GABBERIA PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24-Pgns. W/S Division-I, PHE Dte. for augmentation surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. (SM/14871) | AE SWSD-II | JE2 | ORD/000095/2025-2026 | 1770/SWD-I | 02/07/2025 | 01/08/2025 | SRIJON ENTERPRISE | 10.5 | 0 | 0 | 1
Total | [13 empty] | 635.63 | 248.92 | 39.16