## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,& 3 for Augmentation of Kalikapur Barasat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 1044/SMD | 17/04/2023 | 16/07/2023 | RELIABLE CONSTRUCTION | 35.5 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 3394/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 17.89 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000283/2023-2024 | 2415/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 52.36 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Kalikapur Barasat Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000967/2022-2023 | 1384/SWD-I | 20/09/2022 | 20/10/2022 | GEO SOLUTION | 2.77 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Road restoration of WB024 17, L053 Gudamer Hat to Singher Dari Hugh School |  |  | BILL/01781/2024-2025 | BP-2024-25-806 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 9.76 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for KALIKAPUR BARASAT PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018436] | AE BSD | JE RWS | ORD/000582/2022-2023 | 3067/SWD-I | 21/02/2023 | 23/10/2025 | WATER TECH (E-MAIL :- ENVO.WATERTECH@GMAIL.COM) | 47.69 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Functional Household Tap connection(FHTC) for piped water supply scheme at KALIKAPUR BARASAT Mouza of Joynagar-I Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2904] [TSM/018436] | AE BSD | JE RWS,JE-2 | ORD/000023/2023-2024 | 100/SWD-I | 10/04/2023 | 05/07/2025 | MILAN GHOSH | 363.92 | 0 | 0 | 90
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14872 | Augmentation | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14872) | AE BSD | JE RWS | ORD/000401/2024-2025 | 3681/SWD-I | 22/08/2024 | 10/07/2025 | MILAN GHOSH | 92.68 | 0 | 0 | 50
Total | [13 empty] | 622.56 | 0 | 0