## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Lakshminarayanpur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000960/2022-2023 | 1330/SWD-I | 15/09/2022 | 15/10/2022 | GEO SOLUTION | 2.7 | 2.66 | 98.49 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of LAKSHMINARAYANPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2868] [TSM/018292] | AE BSD | JE-2 | ORD/000102/2023-2024 | 472/SWD-I | 04/05/2023 | 18/04/2026 | M/S A.B. ENTERPRISE | 389.11 | 0 | 0 | 60
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for LAKSHMIKANTAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE SWSD-II |  | ORD/000041/2023-2024 | 106/SWD-I | 10/04/2023 | 25/04/2023 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for LAKSHMINARAYANPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018292] (2nd Call) | AE BSD | JE RWS | ORD/000117/2023-2024 | 529/SWD-I | 11/05/2023 | 10/06/2023 | N.A. ENTERPRISE | 47.62 | 15.2 | 31.91 | 30
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Laxminarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | Assistant Engineer | Junior Engineer | ORD/000046/2023-2024 | 1042/SMD | 17/04/2023 | 26/06/2026 | WEST BENGAL ENGINEERING CO. | 35.49 | 0 | 0 | 30
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 71.11 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Construction of Platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14873) (2nd call) |  |  | ORD/000737/2024-2025 | 4635/SWD-I | 14/11/2024 | 29/12/2024 | ALISHA CONSTRUCTION | 87.6 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different Head Work Sites around South 24-Pgns. for the Engineering Teams of South 24-Pgns. W/S Circle, PHE Dte. under Executive Engineer, South 24-Pgns. Divn.-I, PHE Dte. [SM/14873] [w.e.f. 01/11/2024 to 30/04/2025] [Vehicle No- WB-05-4231] | AE HQ-II | JE-2 | ORD/000875/2024-2025 | 4425/SWD-I | 28/10/2024 | 28/04/2025 | PALASH DAS | 0.86 | 2.34 | 270.59 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. |  |  | BILL/00664/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different Head Work Sites around South 24-Pgns. for the Engineering Teams of South 24-Pgns. W/S Circle, PHE Dte. under Executive Engineer, South 24-Pgns. Divn.-I, PHE Dte. [SM/14873] [w.e.f. 01/05/2025 to 29/10/2025] [Vehicle No- WB-05-4231] |  | JE-2 | ORD/000057/2025-2026 | 1153/SWD-I | 28/04/2025 | 27/10/2025 | PALASH DAS | 0.86 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Lakshminarayanpur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/14873) | Assistant Engineer | Junior Engineer | ORD/000986/2025-2026 | 569-SMSD | 17/04/2025 | 02/05/2025 | WEST BENGAL ENGINEERING CO. | 0.72 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Supply & laying of submersible cable through non metalic pipes for electrical connection of pumping machinery with Pump House no-1 of Lakshminarayanpur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/14873) | Assistant Engineer | Junior Engineer | ORD/000987/2025-2026 | 570/SMSD | 17/04/2025 | 02/05/2025 | WEST BENGAL ENGINEERING CO. | 0.81 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected A | SM/14873 | Augmentation | Quotation for new service connection at P.H. NO.1 of Laxminarayanpur w/s scheme . Application no.1008286424. |  |  | BILL/02620/2024-2025 | BP-2024-25-564 | 28/01/2025 | 28/01/2025 | WBSEDCL | 4.88 | 0 | 0 | 0
Total | [13 empty] | 646.73 | 20.2 | 3.12