## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | SM/14874 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for SARBERIA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017755] | AE BSD |  | ORD/000583/2022-2023 | 3068/SWD-I | 21/02/2023 | 23/03/2023 | WATER TECH (E-MAIL :- ENVO.WATERTECH@GMAIL.COM) | 31.79 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | SM/14874 | Augmentation | Preparation and submission of Detailed Project Report of SARBERIA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000414/2021-2022 | 1967/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.7 | 98.03 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | SM/14874 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Sarberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | Assistant Engineer | Junior Engineer | ORD/000044/2023-2024 | 1040/SMD | 17/04/2023 | 16/07/2023 | A.K.SIKDAR | 22.37 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | SM/14874 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000342/2023-2024 | 261/SWD-I | 10/01/2024 |  | Resource Division | 13.61 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | SM/14874 | Augmentation | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at SARBERIA Mouza of Joynagar-I Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district [No. of FHTC = 2209] [TSM/017755] | AE BSD | JE-1 | ORD/000013/2023-2024 | 32/SWD-I | 05/04/2023 | 04/07/2023 | MILAN GHOSH | 299.38 | 162.12 | 54.15 | 80
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SARBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of S | SM/14874 | Augmentation | Construction of Boundary walls, platform for providing FHTC, development of land, pipeline protection work and other allied works for Ground water based SARBERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14874) |  |  | ORD/000355/2024-2025 | 3455/SWD-I | 02/08/2024 | 16/09/2024 | MILAN GHOSH | 85.25 | 0 | 0 | 0
Total | [13 empty] | 455.16 | 164.82 | 36.21