## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 3393/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 19.59 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 57.67 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Shyampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000053/2023-2024 | 1049/SMD | 17/04/2023 | 16/07/2023 | B.T.PROJECTS PVT.LTD. | 34.89 | 10.54 | 30.22 | 30
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at SHYAMPUR Part-I Mouza of Mograhat-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 3180] [TSM/018169] | AE BSD,AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000288/2023-2024 | 1609/SWD-I | 01/08/2023 | 30/10/2023 | UCON | 433.14 | 123.81 | 28.58 | 25
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for SHYAMPUR (PART-I) PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. | AE RWS, Alipore Division | JE RWS, Magrahat-II Block,JE3 | ORD/000568/2022-2023 | 3064/SWD-I | 21/02/2023 | 23/03/2023 | G M ENTERPRISE (19AQFPM3953P1Z3) | 47.4 | 46.02 | 97.09 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Shyampur(part-I) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000974/2022-2023 | 1427/SWD-I | 22/09/2022 | 22/10/2022 | GEO SOLUTION | 2.74 | 2.74 | 100 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05029/2023-2024 | BP-2023-24-563 | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.58 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Shyampur W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) | Assistant Engineer | Junior Engineer | ORD/001293/2024-2025 | 950/SMSD | 02/07/2024 | 17/07/2024 | B.T.PROJECTS PVT.LTD. | 0.74 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Development of Land, Construction of Boundary wall (length = 48.00m) & Construction of Approach Road (length = 10.00m) at 2nd Tubewell Site for Shyampur Part-I PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I Phe Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14875) | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000417/2024-2025 | 3737/SWD-I | 27/08/2024 | 25/03/2025 | KALAM ENTERPRISE | 8.82 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Dhamua Amratala Road from 2+500 Km to 3+400 Km, from 3+740 Km to 6+410 Km, 7+400 Km to 7+900 Km, Restoration of Damages caused by laying of pipe line by PHE Dte. under Shyampur Part-I PWSS, Dihinarayani PWSS, Chak Haranandapur PWSS under South 24 Parganas Highway Division in the district of South 24 Parganas. |  |  | BILL/00158/2025-2026 |  | 02/06/2025 | 02/06/2025 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 55.67 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMPUR PART 1 piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/14875 | Augmentation | Dhamua Amratala with Link to Ranganberia Road from 7+900 Km to 10+640 Km, Restoratin of Damages caused / to be caused by laying of pipe line by PHE Dte under Shyampur Part-I PWSS, under South 24 Parganas Highway Division in the districtof South 24 Parganas |  |  | BILL/00159/2025-2026 |  | 02/06/2025 | 02/06/2025 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 101.1 | 0 | 0 | 0
Total | [13 empty] | 762.34 | 183.12 | 24.02