## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Uttar Durgapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | Assistant Engineer | Junior Engineer | ORD/000045/2023-2024 | 1041/SMD | 17/04/2023 | 16/07/2023 | WEST BENGAL ENGINEERING CO. | 35.49 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Durgapur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000953/2022-2023 | 1304/SWD-I | 14/09/2022 | 14/10/2022 | GEO SOLUTION | 2.72 | 2.65 | 97.34 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 45.58 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14876) (2nd call) |  |  | ORD/000739/2024-2025 | 4637/SWD-I | 14/11/2024 | 29/12/2024 | SANJAY ENTERPRISE | 82.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR DURGAPUR PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017757] [2nd Call] | AE BSD | JE-1 | ORD/000682/2022-2023 | 3482/SWD-I | 15/03/2023 | 14/04/2023 | KHANDAKAR CONSTRUCTION | 47.64 | 45.33 | 95.17 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Quotation for new power connection at p.h. no.1 of Uttar Durgapur w/s scheme . JL no.-035. Khatian no.-570. Application no.1008598901. |  |  | BILL/00679/2025-2026 |  | 11/06/2025 | 11/06/2025 | WBSEDCL | 7.77 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Quotation for new power connection at P.H. NO.3 of Uttar Durgapur w/s scheme . JL no.-035. Dag no.-92. Application no.1008598948. |  |  | BILL/00676/2025-2026 |  | 11/06/2025 | 11/06/2025 | WBSEDCL | 6.95 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Quotation for new power connection at P.H. NO.2 of Uttar Durgapur w/s scheme . JL no.-036. Dag no.-994. Khatian no.-1361. Application no. 1008598939. |  |  | BILL/00678/2025-2026 |  | 11/06/2025 | 11/06/2025 | WBSEDCL | 14.38 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of UTTAR DURGAPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2779] [TSM/017757] | AE BSD | JE RWS | ORD/000281/2023-2024 | 1567/SWD-I | 27/07/2023 | 11/04/2026 | RELIABLE CONSTRUCTIONS | 358.16 | 3.41 | 0.95 | 53
Total | [13 empty] | 601.29 | 51.39 | 8.55