## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Uttar Durgapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | Assistant Engineer | Junior Engineer | ORD/000045/2023-2024 | 1041/SMD | 17/04/2023 | 16/07/2023 | WEST BENGAL ENGINEERING CO. | 35.49 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Durgapur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000953/2022-2023 | 1304/SWD-I | 14/09/2022 | 14/10/2022 | GEO SOLUTION | 2.72 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 45.58 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14876) (2nd call) |  |  | ORD/000739/2024-2025 | 4637/SWD-I | 14/11/2024 | 29/12/2024 | SANJAY ENTERPRISE | 82.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Area | SM/14876 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR DURGAPUR PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017757] [2nd Call] | AE BSD | JE-1 | ORD/000682/2022-2023 | 3482/SWD-I | 15/03/2023 | 14/04/2023 | KHANDAKAR CONSTRUCTION | 47.64 | 0 | 0 | 100
Total | [13 empty] | 214.03 | 0 | 0