## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based GANGADUARA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000924/2022-2023 | 1177/SWD-I | 31/08/2022 | 30/09/2022 | ASTER CONSULTANCY | 2.68 | 2.66 | 99.21 | 100
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gangaduara ( Zone-43) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 945/SMD | 04/04/2023 | 02/07/2025 | SARKAR ELECTRICAL | 22.38 | 0 | 0 | 40
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of GANGADUARA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1426] [TSM/018365] | AE BSD | JE-1 | ORD/000012/2023-2024 | 31/SWD-I | 05/04/2023 | 01/03/2026 | SUN CONSTRUCTION | 330 | 168.83 | 51.16 | 80
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for GANGADUARA PWSS at Zone-43 of Baruipur block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018365] | AE BSD | JE-1 | ORD/000559/2022-2023 | 3051/SWD-I | 20/02/2023 | 22/03/2023 | DEV & COMPANY (EMAIL ID- DEVANDCOMPANYKOL@GMAIL.COM) | 31.8 | 29.87 | 93.95 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 25.53 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00126/2024-2025 | BP-2024-25-39 | 24/04/2024 | 24/04/2024 | WBSEDCL | 4.82 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gangaduara W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15177) | Assistant Engineer | Junior Engineer | ORD/001639/2024-2025 | 103/SMSD | 21/01/2025 | 05/02/2025 | SARKAR ELECTRICAL | 0.91 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Gangaduara W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15177) | Assistant Engineer | Junior Engineer | ORD/001640/2024-2025 | 101/SMSD | 21/01/2025 | 05/02/2025 | SARKAR ELECTRICAL | 0.58 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gangaduara W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15177) | Assistant Engineer | Junior Engineer | ORD/001641/2024-2025 | 102/SMSD | 21/01/2025 | 05/02/2025 | SARKAR ELECTRICAL | 0.91 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANGADUARA (ZONE-43) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/15177 | Augmentation | Charges for new service connection at pump house no- Gangaduara water supply scheme (Baruipur Block) |  |  | BILL/02414/2024-2025 | BP-2024-25-518 | 10/01/2025 | 10/01/2025 | WBSEDCL | 4.21 | 0 | 0 | 0
Total | [13 empty] | 423.82 | 201.36 | 47.51