## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/15180 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 295/SWD-I | 25/04/2023 |  | Resource Division | 6.56 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/15180 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1& 2 for Augmentation of Malayapur (Zone-24) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 941/SMD | 04/04/2023 | 03/07/2023 | MAA TARA CONSTRUCTION | 22.2 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/15180 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based MALAYAPUR Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000922/2022-2023 | 1174/SWD-I | 31/08/2022 | 30/09/2022 | ASTER CONSULTANCY | 2.57 | 1.28 | 49.85 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/15180 | Augmentation | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALAYPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 841] [TSM/018360] | AE BSD | JE-1 | ORD/000068/2023-2024 | 369/SWD-I | 27/04/2023 | 26/07/2023 | JAI BHARAT COMMERCIAL CORPORATION | 121.47 | 14.93 | 12.29 | 60
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALAYAPUR (ZONE-24) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/15180 | Augmentation | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work, Restoration of road and other allied works for Ground water based MALAYAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15180) |  |  | ORD/000342/2024-2025 | 3316/SWD-I | 23/07/2024 | 06/09/2024 | JAI BHARAT COMMERCIAL CORPORATION | 59.41 | 0 | 0 | 0
Total | [13 empty] | 212.21 | 16.21 | 7.64